## Form 10-A
FDP Form 10a - Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
MUNICIPALITY OF BALUNGAO
1st Quarter, CY 2019
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
to Date
LGU Balungao | Purchase of second Hand Multi-Purpose Vehicle 15CD |  | 400000 | 2019-03-11 | None | 2019-03-25 | 100% | 400000 | Completed
LGU Balungao | Purchase of 9 Units Aircon Ventilating Equipmet 2.5HP w/ unit Installation |  | 822830 | 2019-02-02 | None | 2019-02-26 | 100% | 822830 | Completed
LGU Balungao | Construction of Riverwall Protection 120CD | Rajal- Angayan Norte | 20000000 | 2019-03-17 | None | 2019-07-12 | 65% | 20000000 | On-going
LGU Balungao | Construction of Tricycle Terminal 45CD | Poblacion, Bal. Pang | 1000000 | 2019-03-08 | None | 2019-05-21 | 100% | 1000000 | On-going
LGU Balungao | Opening of Farm to Market Road | Esmeralda- Angayan Sur | 1000000 | 2019-03-08 | None | 2019-03-17 | 100% | 1000000 | Completed
LGU Balungao | Construction of Canal Irrigation System | Angayan Sur | 3200000 | 2019-03-21 | None | 2019-05-04 | 75% | 3200000 | On-going
ENGR. GLACE L. OSOTEO SUSANA I. BALLANO DR. IRENE G. OCAMPO DR. GERARDO U. ACOSTA ANGELITA T. VALERIO
Chairman Vice Chairman |  | Member |  |  |  | Member |  | Member

## Form 10-B
FDP Form 10b - Bid Results on Goods and Services
Republic of the Philippines
GOODS AND SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
1st Quarter, CY 2019
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding | REMARKS
5994661 | Purchase of second Hand Multi-Purpose Vehicle | 400000 | Mary Belle Acob Tullao Trading | Tayug, Pangasinan | 399900 | 2019-02-26 | On-going
5994661 | Purchase of 9 Units Aircon Ventilating Equipmet 2.5HP w/ unit Installation | 822830 | Mary Belle Acob Tullao Trading | Tayug, Pangasinan | 822700 | 2019-02-26 | On-going
5961181 | Construction of Riverwall Protection | 20000000 | Villar General Construction & Supplies | Pugo, La Union | 19989094.09 | 2019-02-07 | On-going
5974511 | Construction of Tricycle Terminal | 1000000 | Villar General Construction & Supplies | Pugo, La Union | 999940.69 | 2019-02-12 | On-going
5974675 | Opening of Farm to Market Road | 1000000 | Villar General Construction & Supplies | Pugo, La Union | 999549.64 | 2019-02-12 | Completed
5974747 | Construction of Canal Irrigation System | 3200000 | Villar General Construction & Supplies | Pugo, La Union | 2504218.6 | 2019-02-12 | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO SUSANA I. BALLANO
Chairman |  |  | Vice-Chairman
DR. IRENE G. OCAMPO ANGELITA T. VALERIO
Member |  |  | Member

## Form 10-C
FDP Form 10c - Bid Results on Consulting Services
Republic of the Philippines
CONSULTING SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
1st Quarter, CY 2019
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration | REMARKS
1 | 5994661 | Purchase of second Hand Multi-Purpose Vehicle | Balungao | 400000 | Mary Belle Acob Tullao Trading | Tayug, Pangasinan | 399900 | 2019-02-26 | 15CD | On-going
2 | 5994661 | Purchase of 9 Units Aircon Ventilating Equipmet 2.5HP w/ unit Installation | Mt. Baluingao Resort | 822830 | Mary Belle Acob Tullao Trading | Tayug, Pangasinan | 822700 | 2019-02-26 | 30CD | On-going
3 | 5961181 | Construction of Riverwall Protection | Rajal- Angayan Norte | 20000000 | Villar General Construction & Supplies | Pugo, La Union | 19989094.09 | 2019-02-07 | 120CD | On-going
4 | 5974511 | Construction of Tricycle Terminal | Poblacion, Bal. Pang | 1000000 | Villar General Construction & Supplies | Pugo, La Union | 999940.69 | 2019-02-12 | 45CD | On-going
5 | 5974675 | Opening of Farm to Market Road | Esmeralda- Angayan Sur | 1000000 | Villar General Construction & Supplies | Pugo, La Union | 999549.64 | 2019-02-12 | 10CD | Completed
6 | 5974747 | Construction of Canal Irrigation System | Angayan Sur | 3200000 | Villar General Construction & Supplies | Pugo, La Union | 2504218.6 | 2019-02-12 | 45CD | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO SUSANA I. BALLANO
Chairman |  |  | Vice-Chairman
DR. IRENE G. OCAMPO ANGELITA T. VALERIO
Member |  |  | Member