## Form 10-A
FDP Form 10a - Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
MUNICIPALITY OF BALUNGAO
2nd Quarter, CY 2019
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
to Date
LGU Balungao | Extension of 2 Units Market Stall for the Mun.Public Market | San Leon, Bal. | 999787.93 | 2018-12-21 | None | 2019-02-20 | 100% | 999787.93 | Completed
LGU Balungao | Const.of MRF Phase II | Poblacion, Bal. | 156000 | 2018-12-21 | None | 2019-01-04 | 100% | 156000 | Completed
LGU Balungao | Rehabilitation of Cabalancian DD | Poblacion, Bal. | 3199753.78 | 2019-02-07 | None | 2019-06-06 | 100% | 3199753.78 | Completed
LGU Balungao | Rehabilitation of Goat House | Poblacion, Bal. | 599851.73 | 2019-01-25 | None | 2019-03-01 | 100% | 599851.73 | Completed
LGU Balungao | Perimeter Fence at the Motorpool | Poblacion, Bal. | 653836.77 | 2019-02-11 | None | 2019-03-01 | 100% | 653836.77 | Completed
LGU Balungao | Installation of Lighting System at the Aud.Mun & National Road | Poblacion, Bal. | 499792.36 | 1/31/19 | None | 2019-03-01 | 100% | 499792.36 | Completed
LGU Balungao | Construction of Signage of Bal. Hilltop Adv. | Balungao, Pangasinan | 299879.4 | 2019-11-01 | None | 2019-03-07 | 100% | 299879.4 | Completed
LGU Balungao | Construction of Line Canal w/ Cover | San Andres, Bal. | 749887.53 | 2019-01-31 | None | 2019-03-29 | 100% | 749887.53 | Completed
LGU Balungao | Construction of Kita-kita SWIP | Kita-Kita, Bal. | 22889492.41 | 2019-01-31 | None | 2019-09-23 | 100% | 22889492.41 | Completed
LGU Balungao | Construction of Esmeralda II SWIP | Esmeralda, Bal. | 15990551.39 | 2019-02-07 | None | 2019-06-14 | 100% | 15990551.39 | Completed
LGU Balungao | Backfilling of Cemetery (Levelling of Cemeter Grounds | San Aurelio 1st, Bal. | 1941207.8 | 2019-02-08 | None | 2019-02-08 | 100% | 1941207.8 | Completed
LGU Balungao | Construction of Stone Masonry | Poblacion, Bal. | 335778.41 | 2019-02-13 | None | 2019-03-04 | 100% | 335778.41 | Completed
LGU Balungao | Construction of Esmeralda SWIP | Esmeralda, Bal. | 762757.5 | 2019-02-01 | None | 2019-02-15 | 100% | 762757.5 | Completed
LGU Balungao | Construction of Drainage Canal | Poblacion, Bal. | 499687.6 | 2019-01-31 | None | 2019-03-02 | 100% | 499687.6 | Completed
LGU Balungao | Concreting of Roads | Kita-Kita Elem. School, Pugaro & Poblacion | 599741.15 | 2019-02-08 | None | 2019-02-15 | 100% | 599741.15 | Completed
LGU Balungao | Leveling & Backfilling of Cemetery Grounds Phse II | Kita-kita, Pugaro & Poblacion, Bal., Pang | 999815.44 | 2019-03-08 | None |  | 100% | 999815.44 | Completed
LGU Balungao | Construction of 2nd Floor Market Stalls Phase V | Poblacion, Bal. |  | 2019-03-23 | None |  |  |  | On-going
LGU Balungao | Establishing of Physical Fitness Center at Municipal Hall | Poblacion, Bal. |  |  | None
LGU Balungao | Concreting of Farm to Market Road |  |  |  | None |  | 100% |  | Completed
LGU Balungao | Construction of San Joaquin Diversion Dam | San Joaquin, Bal., Pang | 7989867.67 |  | None |  | 100% | 7989867.67 | Completed
LGU Balungao | Construction of IrrigationCanals |  |  |  | None
LGU Balungao | Improvement of Mt. Balungao Hot & Cold Spring Resort | Mt. Balungao |  |  | None
LGU Balungao | Concreting of Multi- Purpose Drying Pavement | Mauban, Bal., Pang |  |  | None
LGU Balungao | Rehabilitation of Don Placido |  | 3574740.56 | 2019-01-28 | None |  | 100% | 3574740.56 | Completed
ENGR. GLACE L. OSOTEO SUSANA I. BALLANO DR. IRENE G. OCAMPO DR. GERARDO U. ACOSTA ANGELITA T. VALERIO
Chairman Vice Chairman |  | Member |  |  |  | Member |  | Member

## Form 10-B
FDP Form 10b - Bid Results on Goods and Services
Republic of the Philippines
GOODS AND SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
2nd Quarter, CY 2019
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding | REMARKS
5782965 | Extension of 2 Units Market Stall for the Mun.Public Market | 1000000 | MKM MARKETING | MARC ANTONY K. MENDOZA | 999787.93 | 2019-12-02
5782638 | Const.of MRF Phase II | 156000 | MKM MARKETING | MARC ANTONY K. MENDOZA | 155850 | 2019-12-02
5898609 | Rehabilitation of Cabalancian DD | 3200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3199753.78 | 2019-03-01
5898615 | Rehabilitation of Goat House | 600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 599851.73 | 2019-03-01
5898618 | Perimeter Fence at the Motorpool | 654000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 653836.77 | 2019-03-01
5898619 | Installation of Lighting System at the Aud.Mun & National Road | 500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 499792.36 | 2019-03-01
5898621 | Construction of Signage of Bal. Hilltop Adv. | 300000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 299879.4 | 2019-03-01
5898623 | Construction of Line Canal w/ Cover | 750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 749887.53 | 2019-03-01
5927550 | Construction of Kita-kita SWIP | 22890000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 22889492.41 | 2019-10-01
5927563 | Construction of Esmeralda II SWIP | 15990802.19 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 15990551.39 | 2019-10-01
5927569 | Backfilling of Cemetery (Levelling of Cemeter Grounds | 1941331.8 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1941207.8 | 2019-10-01
5927580 | Construction of Stone Masonry | 336000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 335778.41 | 2019-10-01
5927585 | Construction of Esmeralda SWIP | 763000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 762757.5 | 2019-10-01
5927598 | Construction of Drainage Canal | 500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 499687.6 | 2019-10-01
5974675 | Concreting of Roads | 600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 599741.15 | 2019-10-01
5974529 | Leveling & Backfilling of Cemetery Grounds Phse II | 1000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 999815.44 | 2019-12-02
Concreting of Farm to Market Road
5165974 | Construction of San Joaquin Diversion Dam transfer to San Aurelio 2nd | 8000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 7989867.67
5974354 | Construction of IrrigationCanals | 3199739.55 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2975757.78
5898612 | Rehabilitation of Don Placido | 3575000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3574740.56
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO SUSANA I. BALLANO
Chairman |  |  | Vice-Chairman
DR. IRENE G. OCAMPO ANGELITA T. VALERIO
Member |  |  | Member

## Form 10-C
FDP Form 10c - Bid Results on Consulting Services
Republic of the Philippines
CONSULTING SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
2nd Quarter, CY 2019
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration | REMARKS
|  | Extension of 2 Units Market Stall for the Mun.Public Market | San Leon, bal. Pang | 1000000 | MKM MARKETING | MARC ANTONY K. MENDOZA | 999787.93
|  | Const.of MRF Phase II | Poblacion, Bal. Pang | 156000 | MKM MARKETING | MARC ANTONY K. MENDOZA | 155850
|  | Rehabilitation of Cabalancian DD | Poblacion, Bal. Pang | 3200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3199753.78
|  | Rehabilitation of Goat House | Poblacion, Bal. Pang | 600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 599851.73
|  | Perimeter Fence at the Motorpool | Poblacion, Bal. Pang | 654000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 653836.77
|  | Installation of Lighting System at the Aud.Mun & National Road | Poblacion, Bal. Pang | 500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 499792.36
|  | Construction of Signage of Bal. Hilltop Adv. | Balungap, Pang. | 300000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 299879.4
|  | Construction of Line Canal w/ Cover | San Andres, Bal. Pang | 750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 749887.53
|  | Construction of Kita-kita SWIP | Kita-kita, Bal. Pang | 22890000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 22889492.41
|  | Construction of Esmeralda II SWIP | Esmeralda, Bal. Pang. | 15990802.19 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 15990551.39
|  | Backfilling of Cemetery (Levelling of Cemeter Grounds | San Aurelio 1st, Bal. Pang | 1941331.8 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1941207.8
|  | Construction of Stone Masonry | Poblacion, Bal. Pang | 336000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 335778.41
|  | Construction of Esmeralda SWIP | Emeralda, Bal. Pang. |  | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 762757.5
|  | Construction of Drainage Canal | Poblacion, Bal. Pang | 500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 499687.6
|  | Concreting of Roads | Kita-kita, Pugaro & Pobl;acion | 600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 599741.15
|  | Leveling & Backfilling of Cemetery Grounds Phse II | San Aurelio 1st, Bal. Pang | 1000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 999815.44
|  | Construction of San Joaquin Diversion Dam transfer to San Aurelio 2nd | San Aurelio 2nd, Bal. Pang | 8000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 7989867.67
|  | Construction of IrrigationCanals | Angayan Sur, Bal. Pang | 3199739.55 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2975757.78
|  | Rehabilitation of Don Placido | San Andres, Bal. Pang | 3575000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3574740.56
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Vice-Chairman
GLACE L. OSOTEO SUSANA I. BALLANO
Chairman |  |  | Member
DR. IRENE G. OCAMPO ANGELITA T. VALERIO
Member