## Sheet1
(LGU-BALUNGAO) Annual Procurement Plan for FY 2020
[5 empty] | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Activity/Project)
Code (PAP) | Procurement Program/Project |  | PMO/End User | Mode of Procurement | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
1 | Purchase of Two (2) Units Brand New Drr Rescue Vehicle |  | MDRRMO | Public Bidding | 2020-06-03 | June 30,2020 | 2020-07-13 | 2020-07-16 | Tobacco Excise Tax FY 2016 | 2600000
2 | Purchase of Nego Carts (Negosyante sa Kariton Program) |  | DOLE | Public Bidding | 2020-06-05 | 2020-06-24 | 2020-07-08 | 2020-07-10 | DOLE | 1999620
3 | Construction of Roads at Brgy. Poblacion & San Joaquin |  | Engineering Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2020 | 2499997.1
4 | Improvement of the Balungao Hilltop Adventure |  | Tourism Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2020 | 4999883.72
5 | Construction of New Vegetable Market Shed & Rehabilitation of Old Building at Brgy. San Leon |  | Engineering Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2020 | 3196484.68
6 | Improvement of Physical Fitness Center at Municipal Hall |  | Engineering Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2020 | 2499781.58
7 | Construction of Columbarium at Brgy. San Aurelio 1st |  | Engineering Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2019 | 694842.99
8 | Construction of Brgy. Health Station at Brgy. San Leon |  | Engineering Office | Public Bidding | 2020-04-14 | May 22,2020 | 2020-06-09 | 2020-06-11 | Tobacco Excise Tax FY 2016 | 1199658.9
9 | Improvement of the New Cemetery (Construction of Canopy at the Multi-Level or Apartment Type Inches & Installation of Lighting System) at Brgy. San Aurelio 1st |  | Engineering Office | Public Bidding | 2020-02-25 | 2020-03-16 | 2020-05-04 | 2020-05-14 | 20% MDF 2020 | 2999693.18
10 | Concreting of Farm to Market Road (375m.) at Brgy. San Raymundo |  | Engineering Office | Public Bidding | 2020-04-14 | May 22,2020 | 2020-06-10 | 2020-06-12 | Tobacco Excise Tax FY 2016 | 2999754.28
11 | Concreting of Farm to Market Road (130m.) at Brgy. San Aurelio 3rd |  | Engineering Office | Public Bidding | 2020-04-14 | May 22,2020 | 2020-06-10 | 2020-06-12 | Tobacco Excise Tax FY 2016 | 1039156.3
12 | Concreting of Farm to Market Road (250m.) at Brgy. Rajal |  | Engineering Office | Public Bidding | 2020-04-14 | May 22,2020 | 2020-06-09 | 2020-06-11 | Tobacco Excise Tax FY 2016 | 1999217.58
13 | Concreting of Farm to Market Road (250m.) at Brgy. Angayan Norte |  | Engineering Office | Public Bidding | 2020-04-14 | May 22,2020 | 2020-06-10 | 2020-06-12 | Tobacco Excise Tax FY 2016 | 1999217.58
14 | Concreting of Barangay Health Station at Brgy. San Miguel |  | Engineering Office | Public Bidding | 2020-04-14 | 2020-05-22 | 2020-06-10 | 2020-06-19 | Tobacco Excise Tax FY 2016 | 1599604.1
15 | Concreting of Farm to Market Road (570m.) at Brgy. Capulaan |  | Engineering Office | Public Bidding | 2020-04-14 | 2020-05-22 | 2020-06-09 | 2020-06-11 | Tobacco Excise Tax FY 2016 | 4559349.6
16 | Concreting of Farm to Market Road (100m.) at Brgy. Pugaro |  | Engineering Office | Public Bidding | 2020-06-05 | 2020-06-24 | 2020-07-10 | 2020-07-13 | Tobacco Excise Tax FY 2016 | 799351.58
17 | Concreting of Farm to Market Road (130m.) at Brgy. San Aurelio 1st |  | Engineering Office | Public Bidding | 2020-06-05 | 2020-06-24 | 2020-07-10 | 2020-07-13 | Tobacco Excise Tax FY 2016 | 1039058.84
18 | Concreting of Farm to Market Road (150m.) at Brgy. San Julian |  | Engineering Office | Public Bidding | 2020-06-05 | June 24,2020 | 2020-07-17 | 2020-07-20 | Tobacco Excise Tax FY 2016 | 1199577.19
19 | Concreting of Farm to Market Road (150m.) at Brgy. San Marcelino |  | Engineering Office | Public Bidding | 2020-06-05 | 2020-06-24 | 2020-07-10 | 2020-07-13 | Tobacco Excise Tax FY 2016 | 1199577.19
20 | Concreting of Farm to Market Road (75m. Each) at Brgy. Angayan Sur, San Joaquin, San Aurelio 2nd, Mauban, Esmeralda, Mabini,San Andres, Poblacion, Kita-kita |  | Engineering Office | Public Bidding | 2020-06-05 | June 24,2020 | 2020-07-14 | 2020-07-23 | Tobacco Excise Tax FY 2016 | 5399761.6
21 | Dredging of Zigyab to Orallo SWIP at Brgy. Angayan Sur |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-05 | 2020-11-06 | Calamity Fund 2020 | 699337.42
22 | Improvement & Extension of Angayan Sur SWIP Canal at Brgy. Angayan Sur |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-05 | 2020-11-06 | Calamity Fund 2020 | 249946.9
23 | Dredging of Cabalaybaan Canal at Brgy. San Joaquin |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-05 | 2020-11-06 | Calamity Fund 2020 | 1299984.84
24 | Rehabilitation/Strenghening of Hanging Bridges at Brgy. Capulaan, San Aurelio 2nd, San Leon |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-06 | 2020-11-09 | Calamity Fund 2020 | 2999934.16
25 | Construction of 5 Unit Cottage at Mt. Balungao & Cold Spring Resort at Brgy. San Andres |  | Tourism Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-06 | 2020-11-09 | 2019 Mayor's Office Capital Outlay | 849880.7
26 | Rehabilitation of Market Stalls Phase III (Repair of Ceiling of Roll up) at Brgy. Poblacion |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-06 | 2020-11-09 | 2019 Mayor's Office Capital Outlay | 399954.87
27 | Rehabilitation of Local Access Road of Mabini-Esmeralda Road at Brgy.Mabini |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-06 | 2020-11-09 | LGSF-AMP 2019 | 11622996.17
28 | Procurement of One (1) Unit Garbage Truck |  | Engineering Office | Public Bidding | 2020-10-08 | 2020-10-28 | 2020-11-05 | 2020-11-06 | MDF 20% | 2495000
29 | Construction of Cross Drainage at Brgy. Angayan Norte |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-20 | 2020-11-23 | Calamity Fund-General Fund | 499922.16
30 | Improvement of Farm to Market Road at San Aurelio 3rd |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-19 | 2020-11-20 | Tobacco Excise Tax FY 2016 | 299978.15
31 | Rehabilitation of Banilla Dam at Brgy. Angayan Norte |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-17 | 2020-11-18 | Calamity Fund | 349984.3
32 | Repair of Slope Protection at Brgy. Poblacion |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-19 | 2020-11-20 | Calamity Fund-General Fund | 299935.89
33 | Improvement of Farm to Market Road at San Joaquin to Angayan Norte |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-19 | 2020-11-20 | Calamity Fund-General Fund | 799987.26
34 | Widening of Box culvert at Brgy. San Miguel |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-17 | 2020-11-18 | Calamity Fund-General Fund | 799990.63
35 | Replacement of Old Big Pool at Brgy. Mt. Balungao Resort |  | Tourism Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-17 | 2020-11-18 | 1.CY 2018 Unexpended Balance on 20% Devt. Fund 2.CY 2020 Increase IRA-20% Dev't . Fund. 3. Cy 2020 Increase IRA - Capital Outlay | 4672416.99
36 | Construction of Balay Silangan at Brgy. Poblacion |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-20 | 2020-11-23 | GAD | 1499875.19
37 | Improvement of Multi-Purpose at Brgy. Poblacion |  | Engineering Office | Public Bidding | 2020-10-15 | 2020-11-04 | 2020-11-20 | 2020-11-23 | 1.CY 2020 Mayor's Office Capital Outlay & 2.CY 2020 Increase IRA- Capital Outlay | 4999993.34
38 | Improvement of Mabini Canal Lining at Brgy. San Andres |  | Engineering Office | Public Bidding | 2020-07-08 | 2020-07-28 | 2020-08-19 | 2020-08-21 | D.A. Region 1 | 3168542.13
39 | Improvement of One (1) Stall for Negosyo Center at 2nd Floor Market Stall Phase V |  | Engineering Office | Public Bidding | 2020-10-21 | 2020-11-10 | 2020-11-23 | 2020-11-25 | CY 2020 Increase IRA- Capital Outlay | 399610.52
Prepared By: | [6 empty] | Approved By:
|  | GLACE L. OSOTEO |  | ELISEO B. MENIADO |  |  | MARIA THERESA R. PERALTA
|  | MPDC |  | Municipal Budget |  |  | Municipal Mayor