## pmr
ANNEX B |  | ANNEX A | [19 empty] | Republic of the Philippines
Municipality of Balungao
Pangasinan
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Procurement Monitoring Report as of July 1, 2020 - December 31, 2020
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Improvement of Mabini Canal Lining at Brgy. | [19 empty] | Brgy. San Andres of this municipality | No | Public Bidding |  | 2020-07-08 | 2020-07-15 | 2020-07-28 | 2020-07-28 |  | October 30,2020 | 2020-08-17 | 2020-08-19 | 2020-08-21 | 2020-08-24 | 2020-11-20 |  | DA R1 | 0 |  |  | 0 | [9 empty] | Completed
| San Andres, Balungao, Pangasinan | [36 empty] | 0 |  |  | 0
2 | Dredging of Zigyab to Orallo SWIP at | [19 empty] | Brgy. Angayan Sur of this municipality | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct.28, 2020 | Oct. 28, 2020 |  | October 30,2020 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-09 | 2020-11-20 |  | Calamity Fund | 0 |  |  | 0
| Bgry. Angayan Sur | [36 empty] | 0 |  |  | 0
3 | Improvement of Extension of Angayan Sur | [19 empty] | Brgy. Angayan Sur of this municipality | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-09 | 2020-11-23 |  | Calamity Fund | 0 |  |  | 0
SWIP Canal at Brgy. Angayan sur, Bal. Pang.
4 | Dredging of Cabalaybaan Canal at Brgy. San | [19 empty] | Brgy. San Joaquin of this municipality | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-09 | 2020-11-24 |  | Calamity Fund
Joaquin, Balungao, Pangasinan
5 | Rehabilitation/Strengthening of Hanging Bridges | [19 empty] | Brgy. Capulaan,San Aurelio 2nd & San Leon of this municipality | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-06 | 2020-11-09 | 2020-11-10 | 2020-11-24 |  | Calamity Fund
at Brgy. Capulaan, San Aurelio 2nd, & San Leon,
Balungao, Pangasinan
6 | Construction of 5 Unit Cottage at Mt. Balungao | [19 empty] | Tourism Officee | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-06 | 2020-11-09 | 2020-11-10 | 2020-11-25 |  | Mayor's Office Capital Outlay 2019
Hot & Cold Spring Resort at Brgy. San Andres,
Balungao, Pangasinan
7 | Rehabilitation of Phase III Market Stall at Brgy. | [19 empty] | Engineering Office | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 28,2020 | 2020-11-04 | 2020-11-06 | 2020-11-09 | 2020-11-10 | 2020-11-24 |  | Mayor's Office Capital Outlay 2019
| Poblacion (Repair of Ceiling & Roll - up) at | [36 empty] | 0 |  |  | 0
| Balungao, Pangasinan | [36 empty] | 0 |  |  | 0
8 | Procurement of Garbage Truck | [19 empty] | MDRRM | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-09 | 2020-11-27 |  | MDF 20%
9 | Rehabilitation of Local Access Road of Mabini - | [19 empty] | Brgy. Mabini of this municipality | No | Public Bidding |  | Oct. 8, 2020 | Oct. 14, 2020 | Oct. 28, 2020 | Oct. 28, 2020 | October 29,2020 | October 30,2020 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-10 | 2020-11-20 |  | LGSF-AMP 2019
Esmeralda Road at Brgy. Mabini, Balungao, Pang.
10 | Construction of Cross Grainage at Brgy. Angayan | [19 empty] | Brgy. Angayan Norte of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-20 | 2020-11-23 | 2020-11-24 | 2020-12-08 |  | Calamity Fund-General Fund
| Norte, Balungao, Pangasinan | [36 empty] | 0 |  |  | 0
11 | Improvement of Farm to Market Road at Brgy. San | [19 empty] | Brgy. San Aurelio 3rd of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-19 | 2020-11-20 | 2020-11-23 | 2020-12-07 |  | Calamity Fund-General Fund | 0 |  |  | 0
| Aurelio 3rd, Balungao, Pangasinan | [36 empty] | 0 |  |  | 0
12 | Rehabilitation of Banilla Dam at Brgy. Angyan Norte | [19 empty] | Brgy. Angayan Norte of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-12-03 |  | Calamity Fund-General Fund
Balungao, Pangasinan
13 | Repair of Slope Protection at Brgy. Poblacion, | [19 empty] | Brgy. Poblacion of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-19 | 2020-11-20 | 2020-11-23 | 2020-12-07 |  | Calamity Fund-General Fund
Balungao, Pangasinan
14 | Improvement of Farm to Market Road at Brgy. San | [19 empty] | Brgy. San Joaquin & Angayan Norte of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-19 | 2020-11-18 | 2020-11-23 | 2020-12-11 |  | Calamity Fund-General Fund
Joaquin to Angayan Norte, Balungao, Pangasinan
15 | Widening of Box Culvert at San Miguel, Balungao, | [19 empty] | Brgy. San Miguel of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-12-04 |  | Calamity Fund-General Fund
Pangasinan
16 | Replacement of Old Big Pool at Mt. Balungao, Pangasinan | [19 empty] | Tourism Office | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-23 |  | CY 2018 Unexpended Bal. on 20% Dev't Fund (P 1,383,911.46), CY 2020 Increase on IRA 20% Dev't Fund (P 2,000,000.00), CY 2020 Increase on IRA Capital Outlay (P 1,600,000.00)
17 | Construction of Balay Silangan at Brgy. Poblacion, | [19 empty] | Brgy. Poblacion of this municipality | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-20 | 2020-11-23 | 2020-11-24 | 2020-12-15 |  | GAD
Balungao, Pangasinan
18 | Improvement of Multi-purpose Building at Brgy. | [19 empty] | Engineering Office | No | Public Bidding |  | Oct. 15, 2020 | Oct. 22, 2020 | Nov. 04, 2020 | Nov. 04, 2020 | November 11,2020 | November 12,2020 | 2020-11-16 | 2020-11-20 | 2020-11-23 | 2020-11-24 | 2020-12-21 |  | Capital Outlay
Poblacion , Balungao, Pangasinan
19 | Procurement of One (1) Unit Brand New Water | [19 empty] | MDRRM | No | Public Bidding |  | Nov. 09, 2020 | Nov. 16, 2020 | Dec. 01, 2020 | Dec. 01, 2020 | December 08,2020 | 2021-12-21 | 2020-12-23 | 2021-01-06 | 2021-01-15 | 2021-01-18 |  |  | MDF
Truck of the Municipality of Balungao, Pangasinan
20 | Construction of Early Childhood Care & Development | [19 empty] | MSWD Office | No | Public Bidding |  | Nov. 09, 2020 | Nov. 16, 2020 | Dec. 01, 2020 | Dec. 01, 2020 | December 08,2020 | December 14,2020 | 2020-12-18 | 2020-12-28 | 2021-01-06 | 2021-01-08 |  |  | Eerly Childhood Care & Development (ECCD) Council
Council at Brgy. Poblacion, Balungao, Pangasinan
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 0
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 0
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
RENE F. SORIBEN
[21 empty] | BAC Secretariat | [10 empty] | GLACE L OSOTEO | [10 empty] | MARIA THERESA R. PERALTA
Municipal Mayor

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement