## Form 10-A
FDP Form 10a - Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
MUNICIPALITY OF BALUNGAO
2nd Quarter, CY 2020
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
|  |  |  | (NTP) |  |  |  | to Date
LGU Balungao | Concreting of Farm to Market Road (375M.) | San Raymundo | 2999754.28 | 2020-06-15 | None | July 24,2020 | 100% | 2999754.28 | Completed
LGU Balungao | Concreting of Farm to Market Road (250M.) | Rajal | 1999217.58 | 2020-06-16 | None | July 10,2020 | 100% | 1999217.58 | Completed
LGU Balungao | Concreting of Farm to Market Road (250M.) | Angayan Norte | 1999217.58 | 2020-06-05 | None | July 13,2020 | 100% | 1999217.58 | Completed
LGU Balungao | Concreting of Farm to Market Road (130M.) | San Aurelio 3rd | 1039156.3 | 2020-06-15 | None | July 12,2020 | 100% | 1039156.3 | Completed
LGU Balungao | Concreting of Barangay Health Station | San Miguel | 1559604.1 | 2020-06-12 | None |  |  | 1559604.1 | Completed
LGU Balungao | Concreting of Farm to Market Road (570m.) | Capulaan | 4559349.6 | 2020-06-12 | None | July 23,2020 | 100% | 4559349.6 | Completed
LGU Balungao | Construction of Brgy. Health Station | San Leon | 1199658.9 | 2020-06-12 | None | July 24,2020 | 100% | 1199658.9 | Completed
LGU Balungao | Purchase of Nego Carts (Negosyo sa Kariton Program) | Balungao | 1999620 | 2020-07-14 | None | July 23,2020 | 100% | 1999620 | Completed
LGU Balungao | Purchase of Two (2) units of DRR Rescue Vehicle | Balungao | 2600000 | 7/71/2020 | None | July 24,2020 | 100% | 2600000 | Completed
LGU Balungao | Concreting of Farm to Market Road (150m.) | San Julian | 1199577.19 | 2020-07-22 | None | Auugust 18, 2020 |  | 1199577.19 | Completed
LGU Balungao | Concreting of Farm to Market Road (150m.) | San Marcelino | 1199577.19 |  | None |  | 100% | 1199577.19 | Completed
LGU Balungao | Concreting of Farm to Market Road (130m.) | San Aurelio 1st | 1039058.84 | 2020-07-15 | None | August 12,2020 | 100% | 1039058.84 | Completed
LGU Balungao | Concreting of Farm to Market Road (100m.) | Pugaro | 799351.58 | 2020-07-15 | None | August 4,2020 | 100% | 799351.58 | Completed
LGU Balungao | Concreting of Farm to Market Road (75m.) | Angayan Norte, San Joaquin, San Aurelio 2nd, Mauban, Esmeralda, Mabini, San Andres, Poblacion & Kita-kita (75m.) | 5399761.6 | 2020-07-24 | None | 2020-09-18 | 100% | 5399761.6 | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO |  |  | SUSANA I. BALLANO
Chairman |  |  | Vice-Chairman
DR. IRENE G. OCAMPO |  |  | ANGELITA T. VALERIO
Member |  |  | Member

## Form 10-B
FDP Form 10b - Bid Results on Goods and Services
Republic of the Philippines
GOODS AND SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
2nd Quarter, CY 2020
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding | REMARKS
6964503 | Concreting of Farm to Market Road (375M.) at Brgy. San Raymundo | 3000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2999754.28 | 5/22/2020 | Completed
6964551 | Concreting of Farm to Market Road (250M.) at Rajal | 2000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1999217.58 | 5/22/2020 | Completed
6964607 | Concreting of Farm to Market Road (250M.) at Brgy. Angayan Norte | 2000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1999217.58 | 5/22/2020 | Completed
6964638 | Concreting of Farm to Market Road (130M.) at Brgy. San Aurelio 3rd | 1040000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1039156.3 | 5/22/2020 | Completed
6964423 | Concreting of Barangay Health Station at Brgy. San Miguel | 1560000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1559604.1 | 5/22/2020 | Completed
6964477 | Concreting of Farm to Market Road (570m.) at Brgy. Capulaan | 4560000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4559349.6 | 5/22/2020 | Completed
6964441 | Construction of Brgy. Health Station at Brgy. San Leon | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199658.9 | 5/22/2020 | Completed
7029348 | Purchase of Nego Carts (Negosyo sa Kariton Program) | 2000000 | MC JEB TRADING | GUIA MICU TABORA | 1999620 | 2020-06-24 | Completed
7023640 | Purchase of Two (2) units of DRR Rescue Vehicle | 2600000 | TOYOTA DAGUPAN CITY, INC. | JESSE STEWARD L. ONG | 2600000 | 2020-06-30 | Completed
7028505 | Concreting of Farm to Market Road (150m.) at Brgy San Julian | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199577.19 | 2020-06-24 | Completed
7028542 | Concreting of Farm to Market Road (150m.) at Brgy San Marcelino | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199577.19 | 2020-06-24 | Completed
7028579 | Concreting of Farm to Market Road (130m.) at Brgy. San Aurelio 1st | 1040000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1039058.84 | 2020-06-24 | Completed
7028640 | Concreting of Farm to Market Road (100m.) at Brgy. Pugaro | 800000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 799351.58 | 2020-06-24 | Completed
7028727 | Concreting of Farm to Market Road (75m.) at Brgy. Angayan Norte, San Joaquin, San Aurelio 2nd, Mauban, Esmeralda, Mabini, San Andres, Poblacion & Kita-kita | 5400000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 5399761.6 | 2020-06-24 | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO |  |  | SUSANA I. BALLANO
Chairman |  |  | Vice-Chairman
DR. IRENE G. OCAMPO |  |  | ANGELITA T. VALERIO
Member |  |  | Member

## Form 10-C
FDP Form 10c - Bid Results on Consulting Services
Republic of the Philippines
CONSULTING SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
2nd Quarter, CY 2020
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration | REMARKS
1 | 6964503 | Concreting of Farm to Market Road (375M.) | San Raymundo | 3000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2999754.28 | 5/22/2020 | 45 Days | Completed
2 | 6964551 | Concreting of Farm to Market Road (250M.) | Rajal | 2000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1999217.58 | 5/22/2020 | 30 Days | Completed
3 | 6964607 | Concreting of Farm to Market Road (250M.) | Angayan Norte | 2000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1999217.58 | 5/22/2020 | 30 Days | Completed
4 | 6964638 | Concreting of Farm to Market Road (130M.) | San Aurelio 3rd | 1040000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1039156.3 | 5/22/2020 | 30 Days | Completed
5 | 6964423 | Concreting of Barangay Health Station | San Miguel | 1560000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1559604.1 | 5/22/2020 | 45 CD | Completed
6 | 6964477 | Concreting of Farm to Market Road | Capulaan (570M.) | 4560000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4559349.6 | 5/22/2020 | 60 CD | Completed
7 | 6964441 | Construction of Brgy. Health Station | San Leon | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199658.9 | 5/22/2020 | 45 Days | Completed
8 | 7029348 | Purchase of Nego Carts (Negosyo sa Kariton Program) | Balungao | 2000000 | MC JEB TRADING | GUIA MICU TABORA | 1999620 | June 24,2020 | 15 Days | Completed
9 | 7023640 | Purchase of Two (2) units of DRR Rescue Vehicle | Balungao | 2600000 | TOYOTA DAGUPAN CITY, INC. | JESSE STEWARD L. ONG | 2600000 | June 30,202 | 10 Days | Completed
10 | 7028505 | Concreting of Farm to Market Road (150m.) | San Julian | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199577.19 | June 24,2020 | 30 Days | Completed
11 | 7028542 | Concreting of Farm to Market Road (150m.) | San Marcelino | 1200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1199577.19 | June 24,2020 | 30 Days | Completed
12 | 7028579 | Concreting of Farm to Market Road (130m.) | San Aurelio 1st | 1040000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1039058.84 | June 24,2020 | 30 Days | Completed
13 | 7028640 | Concreting of Farm to Market Road (100m.) | Pugaro | 800000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 799351.58 | June 24,2020 | 21 Days | Completed
14 | 7028727 | Concreting of Farm to Market Road (75m.) | Angayan Norte, San Joaquin, San Aurelio 2nd, Mauban, Esmeralda, Mabini, San Andres, Poblacion & Kita-kita (75m.) | 5400000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 5399761.6 | June 24,2020 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
GLACE L. OSOTEO |  |  |  | SUSANA I. BALLANO
Chairman |  |  |  | Vice-Chairman
DR. IRENE G. OCAMPO |  |  |  | ANGELITA T. VALERIO
Member |  |  |  | Member