## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4TH QUARTER, CY 2020
Province, City or Municipality: BALUNGAO, PANGASINAN
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
|  |  |  | (NTP) |  |  |  | to Date
LGU Balungao | Improvement of Mabini Canal Lining, Balungao, Pangasinan | Mabini | 3872611.6 | 2020-08-24 |  | 2020-11-20 | 100% | 3872611.6 | Completed
LGU Balungao | Dredging of Zigyab to Orralo SWIP | Angayan Sur | 699337.42 | Nov. 9, 2020 |  | 2020-11-21 | 100% | 699337.42 | Completed
LGU Balungao | Improvement & Extension of Angayan Sur Swip Canal | Angayan Sur | 249946.9 | Nov. 5, 2020 |  | 2020-11-23 | 100% | 249946.9 | Completed
LGU Balungao | Dredging of Cabalaybaan Canal | San Joaquin | 1299984.84 | Nov. 9, 2020 |  | 2020-11-24 | 100% | 1299984.84 | Completed
LGU Balungao | Rehabilitation/Strengthening of Hanging Bridges | Capulaan, San Aurelio 3rd, San Leon | 2999934.16 | Nov. 10, 2020 |  | 2020-11-24 | 100% | 2999934.16 | Completed
LGU Balungao | Contruction of 5 Unit Cottage at Mt. Balungao Hot & Cold Spring Resort | San Andres | 849880.7 | Nov. 10, 2020 |  | 2020-11-25 | 100% | 849880.7 | Completed
LGU Balungao | Rehabilitation of Market Stalls Phase III (Repair of Ceiling & Roll up) | Poblacion | 399954.87 | Nov.10, 2020 |  | 2020-11-24 | 100% | 399954.87 | Completed
LGU Balungao | Rehabilitation of Local Access Road of Mabin - Esmeralda Brgy. Road | Mabini | 11622996.17 | 2020-11-11 |  | 2020-11-20 | 100% | 11622996.17 | Completed
LGU Balungao | Procurement of Garbage Truck | Balungao | 2495000 | 2020-11-09 |  | 2020-11-27 | 100% | 2495000 | Completed
LGU Balungao | Improvement of Farm to Market Road | San Joaquin to Angayan Norte | 799987.26 | 2020-11-23 |  | 2020-12-11 | 100% | 799987.26 | Completed
LGU Balungao | Improvement of Multi- Purpose Building | Poblacion | 499999.34 | 2020-11-24 |  | 2020-12-21 | 100% | 499999.34 | Completed
LGU Balungao | Construction of Balay Silangan | Poblacion | 1499875.19 | 2020-11-24 |  | 2020-12-15 | 100% | 1499875.19 | Completed
LGU Balungao | Replacement of old Big pool at the Mt. Balungao Hot & Cold Spring Resort | Balungao | 4983911.46 | 2020-11-19 |  | 2020-11-23 | 100% | 4983911.46 | On-going
LGU Balungao | Widening of Box Culvert | San Miguel | 799990.63 | 2020-11-19 |  | 2020-12-04 | 100% | 799990.63 | Completed
LGU Balungao | Repair of Slope Protection | Poblacion | 299935.89 | 2020-11-23 |  | 2020-11-07 | 100% | 299935.89 | Completed
LGU Balungao | Rehabilitation of Banilla Dam | Angayan Norte | 349984.3 | 2020-11-19 |  | 2020-12-03 | 100% | 349984.3 | Completed
LGU Balungao | Improvement of Farm to Market Road | San aurelio 3rd | 299978.15 | 2020-11-23 |  | 2020-12-07 | 100% | 299978.15 | Completed
LGU Balungao | Construction of Cross Drainage | Angayan Norte | 499922.16 | 2020-11-24 |  | 2020-12-08 | 100% | 499922.16 | Completed
LGU Balungao | Improvement of One (1) Stall for Negosyo Center at 2nd Floor Market Stall Phase V | Poblacion | 399610.52 | 2020-11-26 |  | 2020-12-18 | 100% | 399610.52 | Completed
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor