## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER, CY 2021
Province, City or Municipality: BALUNGAO, PANGASINAN
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
to Date
LGU Balungao | Construction of Poblacion Small Water Impounding Project (SWIP) | Poblacion | 23847744.63 | 2021-03-11 |  |  | 100% | 23847744.63 | Ongoing
LGU Balungao | Improvement if Mt. Balungao Hot & Cold Spring Resort | San Andres | 4999520.29 | 2021-03-11 |  |  | 100% | 4999520.29 | Ongoing
LGU Balungao | Renovation of Sangguniang Bayan Third Floor | Poblacion | 1599967.8 |  |  |  |  | 1599967.8 | Not yet started
LGU Balungao | Construction of Barangay Health Station | Kita-kita | 1499248.76 | 2021-04-29 |  |  | 100% | 1499248.76 | Completed
LGU Balungao | Construction of Barangay Health Station | Angayan Norte | 1499248.76 | 2021-03-29 |  |  | 100% | 1499248.76 | Completed
LGU Balungao | Construction of Barangay Health Station | Mabini | 1499248.76 | 2021-03-29 |  |  | 100% | 1499248.76 | Completed
LGU Balungao | Construction of Barangay Health Station | San Andres | 1499662.46 | 2021-03-29 |  |  | 100% | 1499662.46 | Completed
LGU Balungao | Construction of Barangay Health Station | San Marcelino | 1499662.46 | 2021-04-29 |  |  | 100% | 1499662.46 | Completed
LGU Balungao | Construction of Barangay Health Station | Sa Julian | 1499662.46 | 2021-03-29 |  |  | 100% | 1499662.46 | Completed
LGU Balungao | Concreting of Farm to Market Road | Capulaan (512.5m) | 4099986.87 | 2021-04-08 |  |  | 100% | 4099986.87 | Completed
LGU Balungao | Concreting of Farm to Market Road | Rajal (512.5m) | 4099986.87 | 2021-04-08 |  |  | 100% | 4099986.87 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Aurelio 3rd (500m) | 3999947.37 | 2021-04-06 |  |  | 100% | 3999947.37 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Joaquin (500m) | 3999947.37 | 2021-04-06 |  |  | 100% | 3999947.37 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Leon (500m) | 3999947.37 | 2021-04-13 |  |  | 100% | 3999947.37 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Miguel (500m) | 3999947.37 | 2021-04-13 |  |  | 100% | 3999947.37 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Raymundo (512.5m) | 4099986.87 | 2021-04-12 |  |  | 100% | 4099986.87 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Andres (312.99m) | 2503820.65 | 2021-04-15 |  |  | 100% | 2503820.65 | Completed
LGU Balungao | Concreting of Farm to Market Road | Angayan Norte (200m) | 1599940.92 | 2021-04-15 |  |  | 100% | 1599940.92 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Julian (200m) | 1599940.92 | 2021-04-15 |  |  | 100% | 1599940.92 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Marcelino (200m) | 1599940.92 | 2021-04-15 |  |  | 100% | 1599940.92 | Completed
LGU Balungao | Concreting of Farm to Market Road | Angayan Sur (175m) | 1399999.23 | 2021-04-12 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | Poblacion (175m) | 1399999.23 | 2021-04-15 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | Pugaro (175m) | 1399999.23 | 2021-04-12 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Aurelio 1st (175m) | 1399999.23 | 2021-04-15 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | Mauban | 1399999.23 | 2021-04-15 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | Esmeralda (175m) | 1399999.23 | 2021-04-12 |  |  | 100% | 1399999.23 | Completed
LGU Balungao | Concreting of Farm to Market Road | San Aurleio 2nd (175m) | 1399999.23 | 2021-04-12 |  |  | 100% | 1399999.23 | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor