## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2021
Province, City or Municipality: BALUNGAO, PANGASINAN
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
to Date
LGU Balungao | Improvement of the Municipal Park & Rehabilitation of the Commonwealth & Rizal Monument of the Municipality of Balungao Pangasinan | Poblacion | 7999994.42 | 2021-05-31 |  |  |  | 7999994.42 | On-going
LGU Balungao | Improvement of the New & Old Municipal Cemetery | Balungao, Pangasinan | 3999994.42 |  |  |  |  | 3999994.42
LGU Balungao | First 1,000 Days Program (Dietary Supplementation for Children 6 to 23 Months & Program Women at Balungao, Pangasinan | Esmeralda | 578950 | 2021-06-07 |  |  |  | 578950 | On-going
LGU Balungao | Purchase of Office & Other Supplies to be used by the Different Deparments & Schools of this municipality | Balungao, Pangasinan | 775759 | 2021-06-24 |  |  |  | 775759 | On-going
LGU Balungao | Purchase of ICT Equipment's to be used by the Different Deparments & Schools of this municipality | Balungao, Pangasinan | 422080 | 2021-06-25 |  |  |  | 422080 | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor