## pmr
ANNEX B |  | ANNEX A | [19 empty] | Republic of the Philippines
Municipality of Balungao
Pangasinan
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Procurement Monitoring Report as of January 1, 2021 - June 30, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Construction of Poblacion Small Water Impounding Project (SWIP) at Brgy. Poblacion | [19 empty] | Brgy. Poblacion | NO | Public Bidding |  | 2021-01-28 | 2021-02-04 | 2021-02-16 | 2021-02-16 | 2021-02-23 | 2021-03-21 | 2021-03-01 | 2021-03-05 | 2021-03-08 | 2021-03-10 |  |  |  | 0 |  |  | 0 | [9 empty] | Completed
[38 empty] | 0 |  |  | 0
2 | Improvement of Mt. Balungao Hot & Cold Spring Resort | [19 empty] | Brgy. San Andres | NO | Public Bidding |  | 2021-01-28 | 2021-02-04 | 2021-02-16 | 2021-02-16 | 2021-02-23 | 2021-03-01 | 2021-03-01 | 2021-03-05 | 2021-03-08 | 2021-03-10 |  |  |  | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
3 | Renovation of sangguniang Bayan Third Floor | [19 empty] | Brgy. Poblacion | NO | Public Bidding | [14 empty] | 0 |  |  | 0
4 | Construction of Barangay Health Station at Brgy. Kita-kita | [19 empty] | Brgy. Kita-kita | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
5 | Construction of Barangay Health Station at Brgy. Angayan Norte | [19 empty] | Brgy. Angayan Norte | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-12
6 | Construction of Barangay Health Station at Brgy. Mabini | [19 empty] | Brgy. Mabini | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | March 24,2021 | 2021-03-25 | 2021-03-26 | 2021-03-29
7 | Construction of Barangay Health Station at Brgy. San Andres | [19 empty] | Brgy. San Andres | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
[38 empty] | 0 |  |  | 0
8 | Construction of Barangay Health Station at Brgy. San Julian | [19 empty] | Brgy. San Julian | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
9 | Construction of Barangay Health Station at Brgy. San Marcelino | [19 empty] | Brgy. San Marcelino | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
10 | Concreting of Farm to Market Road at Brgy. Capulaan (512.5m) | [19 empty] | Brgy. Capulaan | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-23 | 2021-03-25 | 2021-03-29 | 2021-03-30 | 2021-04-07 | 2021-04-08
[38 empty] | 0 |  |  | 0
11 | Concreting of Farm to Market Road at Brgy. Rajal (512.5m) | [19 empty] | Brgy. Rajal | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-23 | 2021-03-25 | 2021-03-29 | 2021-03-30 | 2021-04-07 | 2021-04-08 |  |  |  | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
12 | Concreting of Farm to Market Road at Brgy. San Aurelio 3rd (500m) | [19 empty] | Brgy, San Aurelio 3rd | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-23 | 2021-03-25 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-06
13 | Concreting of Farm to Market Road at Brgy. San Joaquin (500m) | [19 empty] | Brgy. San Joaquin | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-24 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
14 | Concreting of Farm to Market Road at Brgy. San Leon (500m) | [19 empty] | Brgy. San Leon | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-07 | 2021-04-08 | 2021-04-12 | 2021-04-13
15 | Concreting of Farm to Market Road at Brgy. San Miguel (500m) | [19 empty] | Brgy. San Miguel | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-07 | 2021-04-08 | 2021-04-12 | 2021-04-13
16 | Concreting of Farm to Market Road at Brgy. San Raymundo (512.5mm) | [19 empty] | Brgy. San Raymundo | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-07 | 2021-04-08 | 2021-04-12 | 2021-04-13
17 | Concreting of Farm to Market Road at Brgy. San Andres (312.99m) | [19 empty] | Brgy. San Andres | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-30 | April 6,2021 | 2021-04-08 | 2021-04-12 | 2021-04-13 | 2021-04-15
18 | Concreting of Farm to Market Road at Brgy. Angayan Norte (200m) | [19 empty] | Brgy. Angayan Norte | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
19 | Concreting of Farm to Market Road at Brgy. San Julian (200m) | [19 empty] | Brgy. San Julian | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
20 | Concreting of Farm to Market Road at Brgy. San Marcelino (200m) | [19 empty] | Brgy. San Marcelino | NO | Public Bidding |  | 2021-02-25 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29
21 | Concreting of Farm to Market Road at Brgy. Angayan Sur (175m) | [19 empty] | Brgy. Angayan Sur | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-12 |  |  |  | 0 |  |  | 0
22 | Concreting of Farm to Market Road at Brgy. Poblacion (175m) | [19 empty] | Brgy. Poblacion | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-08 | April 12,2021 | 2021-04-13 | 2021-04-15
23 | Concreting of Farm to Market Road at Brgy. Pugaro (175m) | [19 empty] | Brgy. Pugaro | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-12
24 | Concreting of Farm to Market Road at Brgy. San Aurelio 1st (175m) | [19 empty] | Brgy. San Aurelio 1st | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-08 | April 12,2021 | 2021-04-13 | 2021-04-15
25 | Concreting of Farm to Market Road at Brgy. Mauban (175m) | [19 empty] | Brgy. Mauban | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-08 | April 12,2021 | 2021-04-13 | 2021-04-15
26 | Concreting of Farm to Market Road at Brgy. Esmeralda (175m) | [19 empty] | Brgy. Esmeralda | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-12
27 | Concreting of Farm to Market Road at Brgy. San Aurelio 2nd (175m) | [19 empty] | Brgy. San Aurelio 2nd | NO | Public Bidding |  | 2021-03-03 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-26 | 2021-03-30 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-12
28 | Improvement of the Municipal Park & Rehabilitation of the Commonwealth & Rizal Monument of the Municipality of Balungao,Pangasinan | [19 empty] | Brgy. Poblacion | NO | Public Bidding |  | 2021-04-27 | 2021-05-04 | 2021-05-17 | 2021-05-17 | 2021-05-19 | 2021-05-20 | 2021-05-25 | 2021-05-27 | 2021-05-28 | 2021-05-31
29 | Improvement of the New Cemetery & Old Municipal Cemetery | [19 empty] | Balungao | NO | Public Bidding |  | 2021-04-27 | 2021-05-04 | 2021-05-17 | 2021-05-17 | 2021-05-24 | May 25- June 23, 2021 | 2021-06-28 | 2021-07-01 | 2021-07-06 | 2021-07-08
30 | First 1,000 Days Program (Dietary Supplementation for Children 6 to 23 Months & Program Women at Balungao, Pangasinan | [19 empty] | Balungao | NO | Public Bidding |  | 2021-04-27 | 2021-05-04 | 2021-05-17 | 2021-05-17 | 2021-05-25 | 2021-05-27 | 2021-05-31 | 2021-06-02 | 2021-06-04 | 2021-06-07
31 | Purchase of Office & Other Supplies to be used by the different department and schools of this municipality | [19 empty] | Balungao | NO | Public Bidding |  | 2021-05-26 | - | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-22 | 2021-06-22 | 2021-06-23 | 2021-06-24
32 | Purchase of ICT Equipment to be used by the different departments and School of this municipality | [19 empty] | Balungao | NO | Public Bidding |  | 2021-05-26 | - | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-22 | 2021-06-22 | 2021-06-24 | 2021-06-25
33 | Provision of Financial Support for Tobacco Farmers | [19 empty] | Balungao | NO | Public Bidding |  | 2021-04-27: -; 2021-05-17: 2021-06-15
Total Alloted Budget of Procurement Activities | [37 empty] | 0
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 0
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: |  |  |  | 2021-06-02: Recommended for Approval by: | [8 empty] | APPROVED:
RENE F. SORIBEN
[21 empty] | BAC Secretariat |  |  |  | 2021-06-02: GLACE L OSOTEO | [8 empty] | MARIA THERESA R. PERALTA
Municipal Mayor

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement