## pmr
ANNEX B |  | ANNEX A | [19 empty] | Republic of the Philippines
Municipality of Balungao
Pangasinan
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Procurement Monitoring Report as of July 1, 2021 - December 31, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | Rehabilitation of Local Access Road of San Julian - San Marcelino Barangay Road | [19 empty] | San Marcelino | No | Public Bidding |  | 2021-08-12 | 2021-08-18 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-06 | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2022-01-10 | 2021-11-27 | LGSF-FA FY 2021 | 0 |  |  | 0 | [9 empty] | Completed
[38 empty] | 0 |  |  | 0
2 | Improvement of the Municipal Park & Rehabilitation of the Commonwealth and Rizal Monument Phase II | [19 empty] | Poblacion | No | Public Bidding |  | 2021-08-12 | 2021-08-18 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-06 | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2021-10-27 | 2021-10-18 | 20% MDF 2021 | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
3 | Rehabilitation of San Aurelio 2nd Footbridge | [19 empty] | San Aurelio 2nd | No | Public Bidding |  | 2021-08-12 | - | 2021-08-31 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-07 | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2021-10-27 | 2021-11-03 | LGSF-FA FY 2020 | 0 |  |  | 0
4 | Construction of Flood Mitigation | [19 empty] | Balungao | No | Public Bidding |  | 2021-09-08 | 2021-09-14 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 2021-10-01 | 2021-10-05 | 2021-10-06 | 2021-10-08 | 2021-10-11 | 2021-11-12 | 2021-11-12 | Calamity Fund
5 | Construction of Cabaroan SWIP | [19 empty] | Esmeralda | No | Public Bidding |  | 2021-10-03 | 2021-10-11 | 2021-10-22 | 2021-10-22 | October 25-26,2021 | October 28,2021 | October 29,2021 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2021-04-23 | 2021-12-01 | FY-2021 DA R1 & Bereau of Soils & Water Management
6 | Construction of 10 Units Egipto SFR & 10 units San Aurelio 1st | [19 empty] | Poblacion | No | Public Bidding |  | 2021-10-03 | 2021-10-11 | 2021-10-22 | 2021-10-22 | October 25,2021 | October 26,2021 | October 29,2021 | 2020-11-02 | 2020-11-04 | 2020-11-05 | 2021-12-04 | 2021-12-01 | Bereau of Soils & Water Management
7 | Procurement of Conference Table, Chair & Sound System to SK Federation Building | [19 empty] | Poblacion | No | Public Bidding |  | 2021-10-26 | - | 2021-11-16 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-30 | 2021-12-26 | Trust Fund
[38 empty] | 0 |  |  | 0
8 | Improvement of Agriculture Office (Extension at the Front & Back of the Building) | [19 empty] | Poblacion | No | Public Bidding |  | 2021-10-28 | - | 2021-11-18 | 2021-11-18 | 2021-11-19 | 2021-11-22 | 2021-11-25 | 2020-11-26 | 2020-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-17 | 2021 Mayor's Office Capital Outlay
9 | Installation of Water Source & Water System (SK Federation Building, Senior Citizen Federation Building, ECCD Building, San Leon public Market of the Municipality of Balungao, Pangasinan | [19 empty] | Balungao | No | Public Bidding |  | 2021-10-28 | - | 2021-11-18 | 2021-11-18 | 2021-11-19 | 2021-11-22 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-17 | 2021 Mayor's Office Capital Outlay
10 | Improvement of the Electrical Facilities Separation of Matering Box: SK Federation Building, SB Building, PNP Building Municipal Gymnasium | [19 empty] | Poblacion | No | Public Bidding |  | 2021-10-28 | - | 2021-11-18 | 2021-11-18 | 2021-11-19 | November 12,2020 | 2020-11-16 | 2020-11-26 | 2021-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-20 | 2021 Mayor's Office Capital Outlay
[38 empty] | 0 |  |  | 0
11 | Purchase of Office Supplies ICT, Medical Supplies & Other Supplies & Materials to be used by the different offices & School of this municipality | [19 empty] | Balungao | No | Public Bidding |  | 2021-11-04 | 2021-11-10 | 2021-11-23 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-07 | 2021-12-26 | General Fund, Trust Fund & SEF | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
12 | Purchase of ICT Equipments ti be used by the different Offices & Schools of this muncipality | [19 empty] | Balungao | No | Public Bidding |  | 2021-11-04 | - | 2021-11-23 | 2021-11-23 | 2021-11-24 | November 25,2020 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-07 | 2021-12-26 | General Fund& SEF
13 | Construction of Flood Mitigation (Phase II) | [19 empty] | Balungao | No | Public Bidding |  | 2021-11-06 | 2021-11-12 | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-30 | 2021-12-20 | Mayor's Office 2021 Capital Outlay
14 | Improvement of Isolation Facility | [19 empty] | Poblacion | No | Public Bidding |  | 2021-11-06 | - | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-30 | 2021-12-20 | 2021 Calamity Fund
15 | Construction of Slope Protection at Sitio Langto | [19 empty] | Poblacion | No | Public Bidding |  | 2021-11-06 | 2021-11-12 | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2022-01-04 | 2021-12-20 | FY-2021 DA R1 & Bereau of Soils & Water Management
16 | Construction of Material Recovery Facility Expansion | [19 empty] | Poblacion | No | Public Bidding |  | 2021-11-06 | - | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-20 | 2021-12-20 | DENR
17 | Improvement of RHU Facilities (Extension at the Right Side of the Municipal Health Officer & Birthing Clinic & Water System Improvement) of this municipality | [19 empty] | Poblacion | No | Public Bidding |  | 2021-11-06 | 2021-11-12 | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-29 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-30 | 2021-12-27 | GAD
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 0
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 0
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [9 empty] | 2021-12-01: Recommended for Approval by: | [6 empty] | APPROVED:
RENE F. SORIBEN
[21 empty] | BAC Secretariat | [9 empty] | 2021-12-01: GLACE L OSOTEO | [6 empty] | MARIA THERESA R. PERALTA
Municipal Mayor

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement