## Sheet1
Republic of the Philippines
MUNICIPALITY OF BALUNGAO
Province of Pangasinan
Supplemental Procurement Plan (2nd Semester, CY 2021)
CODE (PAP) | Procurement Program/Project | PMO/End User | Mode of Procurement | Actual Procurement Activity | [7 empty] | Remarks
|  |  |  | Ads/Post of IB/ REI | Sub/Open of Bids | Notice of Award | Contract of Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds
1 | Rehabilitation of Local Access Road of San Julian - San Marcelino Barangay Road | San Marcelino | Public Bidding | 2021-08-12 | 2021-08-31 | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2022-01-10 | 2021-11-27 | LGSF-FA FY 2021
2 | Rehabilitation of San Aurelio 2nd Footbridge | San Aurelio 2nd | Public Bidding | 2021-08-12 | 2021-08-31 | 2021-09-08 | 2021-09-10 | 2021-09-13 | 2021-10-27 | 2021-11-03 | LGSF-FA FY 2020
3 | Construction of Flood Mitigation | Balungao | Public Bidding | 2021-08-12 | 2021-08-31 | 2021-10-06 | 2021-10-08 | 2021-10-11 | 2021-11-12 | 2021-11-12 | Calamity Fund
4 | Construction of Cabaroan SWIP | Esmeralda | Public Bidding | 2021-09-08 | 2021-09-28 | 2021-11-03 | 2021-11-04 | 2020-11-05 | 2021-04-23 | 2021-12-01 | FY-2021 DA R1 & Bereau of Soils & Water Management
5 | Construction of 10 Units Egipto SFR & 10 units San Aurelio 1st | Poblacion | Public Bidding | 2021-10-03 | 2021-10-22 | 2021-11-02 | 2021-11-04 | 2020-11-05 | 2021-12-04 | 2021-12-01 | Bereau of Soils & Water Management
6 | Procurement of Conference Table, Chair & Sound System to SK Federation Building | Poblacion | Public Bidding | 2021-10-26 | 2021-10-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-30 | 2021-12-26 | Trust Fund
7 | Improvement of Agriculture Office (Extension at the Front & Back of the Building) | Poblacion | Public Bidding | 2021-10-28 | 2021-11-16 | 2021-11-26 | 2021-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-17 | 2021 Mayor's Office Capital Outlay
8 | Installation of Water Source & Water System (SK Federation Building, Senior Citizen Federation Building, ECCD Building, San Leon public Market of the Municipality of Balungao, Pangasinan | Balungao | Public Bidding | 2021-10-28 | 2021-11-18 | 2021-11-26 | 2021-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-17 | 2021 Mayor's Office Capital Outlay
9 | Improvement of the Electrical Facilities Separation of Matering Box: SK Federation Building, SB Building, PNP Building Municipal Gymnasium | Poblacion | Public Bidding | 2021-10-28 | 2021-11-18 | 2021-11-26 | 2021-11-29 | 2020-12-01 | 2021-12-20 | 2021-12-20 | 2021 Mayor's Office Capital Outlay
10 | Purchase of Office Supplies ICT, Medical Supplies & Other Supplies & Materials to be used by the different offices & School of this municipality | Balungao | Public Bidding | 2021-11-04 | 2021-11-18 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-07 | 2021-12-26 | General Fund, Trust Fund & SEF
11 | Purchase of ICT Equipments ti be used by the different Offices & Schools of this muncipality | Balungao | Public Bidding | 2021-11-04 | 2021-11-23 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-07 | 2021-12-26 | General Fund& SEF
12 | Construction of Flood Mitigation (Phase II) | Balungao | Public Bidding | 2021-11-06 | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-30 | 2021-12-20 | Mayor's Office 2021 Capital Outlay
13 | Improvement of Isolation Facility | Poblacion | Public Bidding | 2021-11-06 | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-30 | 2021-12-20 | 2021 Calamity Fund
14 | Construction of Slope Protection at Sitio Langto | Poblacion | Public Bidding | 2021-11-06 | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2022-01-04 | 2021-12-20 | FY-2021 DA R1 & Bereau of Soils & Water Management
15 | Construction of Material Recovery Facility Expansion | Poblacion | Public Bidding | 2021-11-06 | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-20 | 2021-12-20 | DENR
16 | Improvement of RHU Facilities (Extension at the Right Side of the Municipal Health Officer & Birthing Clinic & Water System Improvement) of this municipality | Poblacion | Public Bidding | 2021-11-06 | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-30 | 2021-12-27 | GAD
Prepared By: |  |  |  |  | Approved By:
| GLACE L. OSOTEO | GLORIA C. FERNANDEZ |  |  | MARIA THERESA R. PERALTA
| MPDC | Municipal Budget |  |  | Municipal Mayor

## Sheet2
LGSF-FA FY 2021
LGSF-FA FY 2020
Calamity Fund
FY-2021 DA R1 & Bereau of Soils & Water Management
Bereau of Soils & Water Management
Trust Fund
2021 Mayor's Office Capital Outlay
2021 Mayor's Office Capital Outlay
2021 Mayor's Office Capital Outlay
General Fund, Trust Fund & SEF
General Fund& SEF
Mayor's Office 2021 Capital Outlay
2021 Calamity Fund
FY-2021 DA R1 & Bereau of Soils & Water Management
DENR
GAD