## FORM 10-A
FDP Form 10a - Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
MUNICIPALITY OF BALUNGAO
4th Quarter, CY 2021
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
|  |  |  | (NTP) |  |  |  | to Date
LGU-BALUNGAO | Construction of Cabaroan SWIP at Brgy. Esmeralda | Esmeralda | 12999909.44 | 2021-11-05 | N/A | 2022-04-23 | 100 | 12999909.44 | Completed
LGU-BALUNGAO | Construction of 10 Units Egipto SFR & 10 units at San Andres & San Aurelio 1st | San Andres & San Aurelio 1st | 2000000 | 2021-11-05 | N/A | 2021-12-04 | 100 | 2000000 | Completed
LGU-BALUNGAO | Procurement of Conference Table, Chairs & Sounds System to SK Federation Building at Brgy. Poblacion, Balungao, pangasinan | Balungao | 200000 | 2021-11-25 | N/A | 2021-11-30 | 100 | 200000 | Completed
LGU-BALUNGAO | Improvement of Agriculture Office (Extension at the Front & Back of the Building) at Brgy. Poblacion | Balungao | 749992 | 2021-12-01 | N/A | 2021-12-20 | 100 | 749992 | Completed
LGU-BALUNGAO | Construction of Flood Mitigation (Phase II) | Balungao | 2524995 | 2021-12-06 | N/A | 2021-12-30 | 100 | 2524995 | Completed
LGU-BALUNGAO | Improvement of Isolation Facility | Poblacion | 699994 | 2021-12-06 | N/A | 2021-12-30 | 100 | 699994 | Completed
LGU-BALUNGAO | Constrution of Slope Protection at Sitio Langto & Sitio Decrito | Esmeralda | 1548668 | 2021-12-06 | N/A | 2022-01-04 | 100 | 1548668 | Completed
LGU-BALUNGAO | Construction of Material Recovery Facility Expansion | Poblacion | 199996 | 2021-12-06 | N/A | 2021-12-20 | 100 | 199996 | Completed

## FORM 10-C
FDP Form 10c - Bid Results on Consulting Services
Republic of the Philippines
CONSULTING SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
4th Quarter, CY 2021
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration | REMARKS
NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE

## FORM 10-B
FDP Form 10b - Bid Results on Goods and Services
Republic of the Philippines
GOODS AND SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
4th Quarter, CY 20201
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding | REMARKS
8127084 | Installation of Water Source & Water System (SK Federation Building, Senior Citizen Federation Building, ECCD Building, San Leeon Public Market of the Municipality Balungao, Pangasinan | 370000 | VILLAR GENERAL CONSTRUCTION & SUPPLIES | BELLAFLOR V. CORPUZ | 369993 | 2021-11-18 | Completed
8127179 | Improvement of the Electrical Facilities Separation of Metering Box: SK Federation Building, Senior Citizen Federation Building, ECCD Building, SB Building, PNP Building Municipal Gymnasium | 300000 | JHI CONSTRUCTION & SUPPLY | TACLIN I. INIBA | 299998 | 2021-11-18 | Completed
8148702 | Purchase of Office Supplies ICT, Medical Supplies & Other Supplies & Materials to be used by the different offices & School of this Municipality | 1398615.57 | MKM MARKETING | MARC ANTHONY K. MENDOZA | 1398165.57 | 2021-11-23 | Completed
8149051 | Purchase of ICT Equipments to be used by the different Offices & Schools of this muncipality | 316079.5 | MKM MARKETING | MARC ANTHONY K. MENDOZA | 315991.5 | 2021-11-24 | Completed
8157576 | Improvement of RHU Facilities (Extension at the Right Side of the Municipal Health Officer & Birthing Clinic & Water System Improvement) of this municipality | 1375000 | JHI CONSTRUCTION & SUPPLY | TACLIN I. INIBA | 1374992 | 2021-11-25 | Completed