## Form 10-A
FDP Form 10a - Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
MUNICIPALITY OF BALUNGAO
1st Quarter, CY 2022
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status |  | Remarks
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred
|  |  |  | (NTP) |  |  |  | to Date
LGU Balungao | Construction of Farm to Market Road | Capulaan | 9099823.29 | 2022-02-09 |  | 2022-04-24 | 100% | 9099823.29 | Completed
LGU Balungao | Construction of Farm to Market Road | San Leon | 3499860.82 | 2022-02-09 |  | 2022-04-24 | 100% | 3499860.82 | Completed
LGU Balungao | Construction of Farm to Market Road | San Marcelino | 4999885.18 | 2022-02-08 |  | 2022-04-23 | 100% | 4999885.18 | Completed
LGU Balungao | Construction of Farm to Market Road | San Aurelio 1st | 2449889.15 | 2022-02-08 |  | 2022-03-14 | 100% | 2449889.15 | Completed
LGU Balungao | Purchase of 200 Units of Sprayers Distributed to Tobacco Farmers of Municipality of Balungao, Pangasinan | Balungao | 750000 | 2022-02-07 |  | 2022-02-16 | 100% | 750000 | Completed
LGU Balungao | Purchase of 64 Units Water Pump to Tobacco Farmers Association of Municipality of Balungao, Pangasinan | Balungao | 1273600 | 2022-02-07 |  | 2022-02-16 | 100% | 1273600 | Completed
LGU Balungao | Construction of Farm to Market Road | Esmeralda | 1049781.2 | 2022-02-09 |  | 2022-03-10 | 100% | 1049781.2 | Completed
LGU Balungao | Purchase of Black Plastic to Tobacco Growers of this municipality | Balungao | 2499000 | 2022-02-24 |  | 2022-03-10 | 100% | 2499000 | Completed
LGU Balungao | Improvement of Municipal Park, Balungao, Pangasinan | Balungao | 2999699.23 | 2022-02-28 |  | 2022-04-13 | 100% | 2999699.23 | Completed
LGU Balungao | Fabrication of Doors & Windows Railing at the Municipal Health Office Birthing Clinic Comelec | Balungao | 239601.82 | 2022-02-28 |  | 2022-03-19 | 100% | 239601.82 | Completed
LGU Balungao | Improvement of Legislative Building | Balungao | 1499940 | 2022-02-24 |  | 2022-03-25 | 100% | 1499940 | Completed
LGU Balungao | Improvement of Mt. Balungao at Brgy. San Andres | San Andres | 2499691.14 | 2022-02-16 |  | 2022-04-01 | 100% | 2499691.14 | Completed
LGU Balungao | Construction/Rehabilitation of Balungao Public Market, Balungao, Pangasinan | Balungao | 3999717.23 | 2022-02-28 |  |  |  | 3999717.23 | On-Going
LGU Balungao | Construction of Flood Mitigation Structure of the Municipality of Balunga, Pangasinan | Balungao | 4999524.23 | 2022-03-03 |  |  |  | 4999524.23 | On-Going
LGU Balungao | Construction of Farm to Market Road | Pugaro | 1049810.38 |  |  |  |  | 1049810.38 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Poblacion | 1049885.15 | 2022-02-11 |  | 2022-03-12 | 100% | 1049885.15 | Completed
LGU Balungao | Construction of Farm to Market Road | San Andres | 1049923.26 | 2022-02-11 |  | 2022-03-12 | 100% | 1049923.26 | Completed
LGU Balungao | Construction of Farm to Market Road | San Joaquin | 1049895.23 | 2022-02-15 |  | 2022-03-16 | 100% | 1049895.23 | Completed
LGU Balungao | Construction of Farm to Market Road | Capulaan | 9262600.14 |  |  |  |  | 9262600.14 | Completed
LGU Balungao | Construction of Farm to Market Road | Rajal | 5599843.03 | 2022-02-16 |  | 2022-05-01 | 100% | 5599843.03 | Completed
LGU Balungao | Construction of Farm to Market Road | Angayan Norte | 5599861.47 | 2022-02-15 |  | 2022-04-30 | 100% | 5599861.47 | Completed
LGU Balungao | Construction of Farm to Market Road | San Leon | 4199862.97 | 2022-02-15 |  | 2022-04-30 | 100% | 4199862.97 | Completed
LGU Balungao | Construction of Farm to Market Road | San Marcelino | 4999835.07 | 2022-02-16 |  | 2022-05-01 | 100% | 4999835.07 | Completed
LGU Balungao | Construction of Farm to Market Road | San Aurelio 1st | 4199874.52 | 2022-02-23 |  | 2022-05-08 | 100% | 4199874.52 | Completed
LGU Balungao | Construction of Farm to Market Road | Esmeralda | 1049815.85 | 2022-02-23 |  | 2022-03-24 | 100% | 1049815.85 | Completed
LGU Balungao | Construction of Farm to Market Road | San Andres | 1049891.45 | 2022-02-23 |  | 2022-03-17 | 100% | 1049891.45 | Completed
LGU Balungao | Livelihood Program (Purchase of Food Stand of this Municipality | Balungao | 736037.23 | 2022-02-28 |  | 2022-03-19 | 100% | 736037.23 | Completed
LGU Balungao | Construction of Farm to Market Road | San Joaquin | 1049887.9 | 2022-02-24 |  | 2022-03-25 | 100% | 1049887.9 | Completed
LGU Balungao | Construction of Farm to Market Road | San Raymundo | 8749826.75 | 2022-02-16 |  | 2022-05-22 | 45% | 3937422.04 | On-Going
LGU Balungao | Construction of Farm to Market Road | San Raymundo | 7472845.95 | 2022-02-09 |  | 2022-04-24 | 60% | 4483707.57 | On-Going
LGU Balungao | Dietary Supplementation of Expectant Mothers & Children of this municipality | Balungao | 699900 | 2022-02-28 |  | 2022-05-28 | 16% | 109650 | On-Going
LGU Balungao | Electrification Along Pugaro Napudot Road, Balungao, Pangasinan | Balungao | 5499678.33 |  |  |  |  | 5499678.33 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Angayan Sur | 1049898.54 |  |  |  |  | 1049898.54 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Kita-kita | 1049804.89 |  |  |  |  | 1049804.89 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Mauban | 1049883.37 |  |  |  |  | 1049883.37 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Mabini | 1049887.14 |  |  |  |  | 1049887.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Poblacion | 1049862.05 |  |  |  |  | 1049862.05 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Aurelio 2nd | 1049851 |  |  |  |  | 1049851 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Miguel | 7473261.75 |  |  |  |  | 7473261.75 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Rajal | 4899858.31 |  |  |  |  | 4899858.31 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Angayan Norte | 4899872.73 |  |  |  |  | 4899872.73 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Aurelio 3rd | 4199883.54 |  |  |  |  | 4199883.54 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Julian | 4199843.81 |  |  |  |  | 4199843.81 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Pugaro | 2449890.33 |  |  |  |  | 2449890.33 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Angayan Sur | 1049896.48 |  |  |  |  | 1049896.48 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Aurelio 2nd | 1049849.31 |  |  |  |  | 1049849.31 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Miguel | 8749780.76 |  |  |  |  | 8749780.76 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Aurelio 3rd | 4899863.03 |  |  |  |  | 4899863.03 | Not yet started
LGU Balungao | Construction of Farm to Market Road | San Julian | 4199797.19 |  |  |  |  | 4199797.19 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Kita-kita | 1049865.14 |  |  |  |  | 1049865.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Mauban | 1049889.14 |  |  |  |  | 1049889.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road | Mabini | 1049901.74 |  |  |  |  | 1049901.74 | Not yet started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor

## Form 10-B
FDP Form 10b - Bid Results on Goods and Services
Republic of the Philippines
GOODS AND SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
1st Quarter, CY 2022
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding | REMARKS
8333944 | Construction of Farm to Market Road at Brgy. Capulaan | 9100000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 9099823.29 | 2022-01-25 | Completed
8334096 | Construction of Farm to Market Road at Brgy. San Leon | 3500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3499860.82 | 2022-01-25 | Completed
8334107 | Construction of Farm to Market Road at Brgy. San Marcelino | 5000000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 499885.18 | 2022-01-25 | Completed
8334116 | Construction of Farm to Market Road at Brgy. San Aurelio 1st | 2450000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 2449889.15 | 2022-01-25 | Completed
8333815 | Purchase of 200 Units of Sprayers Distributed to Tobacco Farmers of Municipality of Balungao, Pangasinan | 760000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 750000 | 2022-01-25 | Completed
8333869 | Purchase of 64 Units Water Pump to Tobacco Farmers Association of Municipality of Balungao, Pangasinan | 1280000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 1273600 | 2022-01-25 | Completed
8338416 | Construction of Farm to Market Road at Brgy. Esmeralda | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049781.2 | 2022-01-26 | Completed
8366157 | Purchase of Black Plastic to Tobacco Growers of this municipality | 2500000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 2499000 | 2022-01-10 | Completed
8368265 | Improvement of Municipal Park, Balungao, Pangasinan | 3000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2999699.23 | 2022-02-14 | Completed
8368898 | Fabrication of Doors & Windows Railing at the Municipal Health Office Birthing Clinic Comelec | 240000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 239601.82 | 2022-01-14 | Completed
8368978 | Improvement of Legislative Building | 1600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1499940 | 2022-02-14 | Completed
8368367 | Improvement of Mt. Balungao at Brgy. San Andres | 2500000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 2499691.14 | 2022-02-14 | Completed
8368299 | Construction/Rehabilitation of Balungao Public Market, Balungao, Pangasinan | 4000000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 3999717.23 | 2022-02-14 | Completed
8368510 | Construction of Flood Mitigation Structure of the Municipality of Balunga, Pangasinan | 5000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4999524.23 | 2022-02-14 | Completed
8364568 | Construction of Farm to Market Road at Brgy. Pugaro | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049810.38 | 2022-02-10 | Completed
8338505 | Construction of Farm to Market Road at Brgy. Poblacion | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049885.15 | 2022-01-26 | Completed
8349843 | Construction of Farm to Market Road at Brgy. San Andres | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049923.26 | 2022-02-02 | Completed
8349905 | Construction of Farm to Market Road at Brgy. San Joaquin | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049895.23 | 2022-02-02 | Completed
8349981 | Construction of Farm to Market Road at Brgy. Capulaan | 9262752 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 9262600.14 | 2022-02-02 | Completed
8350089 | Construction of Farm to Market Road at Brgy. Rajal | 5600000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 5599843.03 | 2022-02-02 | Completed
8350149 | Construction of Farm to Market Road at Brgy. Angayan Norte | 5600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 5599861.47 | 2022-02-02 | Completed
8350248 | Construction of Farm to Market Road at Brgy. San Leon | 4200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4199862.97 | 2022-02-02 | Completed
8350276 | Construction of Farm to Market Road at Brgy. San Marcelino | 5000000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4999835.07 | 2022-02-02 | Completed
8364485 | Construction of Farm to Market Road at Brgy. San Aurelio 1st | 4200000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 4199874.52 | 2022-02-10 | Completed
8364674 | Construction of Farm to Market Road at Brgy. Esmeralda | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049815.85 | 2022-02-10 | Completed
8366022 | Construction of Farm to Market Road at Brgy. San Andres | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049891.45 | 2022-02-10 | Completed
8368477 | Livelihood Program (Purchase of Food Stand of this Municipality | 736264.6 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 736037.23 | 2022-02-14 | Completed
8366064 | Construction of Farm to Market Road at Brgy. San Joaquin | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049887.9 | 2022-02-10 | Completed
8350046 | Construction of Farm to Market Road at Brgy. San Raymundo | 8750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 8749826.75 | 2022-02-02 | On-Going
8333988 | Construction of Farm to Market Road at Brgy. San Raymundo | 7473423.54 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 7472845.95 | 2022-01-25 | On-Going
8368213 | Dietary Supplementation of Expectant Mothers & Children of this municipality | 700000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 699900 | 2022-01-14 | On-Going
8368243 | Electrification Along Pugaro Napudot Road, Balungao, Pangasinan | 5500000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 5499678.33 | 2022-02-14 | On-Going
8364619 | Construction of Farm to Market Road at Brgy. Angayan Sur | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049898.54 | 2022-02-10 | Not yet started
8365862 | Construction of Farm to Market Road at Brgy. Kita-kita | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049804.89 | 2022-02-10 | Not yet started
8365937 | Construction of Farm to Market Road at Brgy. Mauban | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049883.37 | 2022-02-10 | Not yet started
8365970 | Construction of Farm to Market Road at Brgy. Mabini | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049887.14 | 2022-02-10 | Not yet started
8365997 | Construction of Farm to Market Road at Brgy. Poblacion | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049862.05 | 2022-02-10 | Not yet started
8366044 | Construction of Farm to Market Road at Brgy. San Aurelio 2nd | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049851 | 2022-02-10 | Not yet started
833953 | Construction of Farm to Market Road at Brgy. San Miguel | 7473423.45 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 7473261.75 | 2022-01-25 | Not yet started
8334020 | Construction of Farm to Market Road at Brgy. Rajal | 4900000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4899858.31 | 2022-01-25 | Not yet started
8334038 | Construction of Farm to Market Road at Brgy. Angayan Norte | 4900000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4899872.73 | 2022-01-25 | Not yet started
8334053 | Construction of Farm to Market Road at Brgy. San Aurelio 3rd | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199883.54 | 2022-01-25 | Not yet started
8334069 | Construction of Farm to Market Road at Brgy. San Julian | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199843.81 | 2022-01-25 | Not yet started
8338335 | Construction of Farm to Market Road at Brgy. Pugaro | 2450000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2449890.33 | 2022-01-26 | Not yet started
8338378 | Construction of Farm to Market Road at Brgy. Angayan Sur | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049896.48 | 2022-01-26 | Not yet started
8349871 | Construction of Farm to Market Road at Brgy. San Aurelio 2nd | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049849.31 | 2022-02-02 | Not yet started
8350012 | Construction of Farm to Market Road at Brgy. San Miguel | 8750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 8749780.76 | 2022-02-02 | Not yet started
8350173 | Construction of Farm to Market Road at Brgy. San Aurelio 3rd | 4900000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4899863.03 | 2022-02-02 | Not yet started
8350231 | Construction of Farm to Market Road at Brgy. San Julian | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199797.19 | 2022-02-02 | Not yet started
8338428 | Construction of Farm to Market Road at Brgy. Kita-kita | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049865.14 | 2022-01-26 | Not yet started
8338456 | Construction of Farm to Market Road at Brgy. Mauban | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049889.14 | 2022-01-26 | Not yet started
8338484 | Construction of Farm to Market Road at Brgy. Mabini | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049901.74 | 2022-01-26 | Not yet started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor

## Form 10-C
FDP Form 10c - Bid Results on Consulting Services
Republic of the Philippines
CONSULTING SERVICES BID-OUT
Province, City or Municipality: BALUNGAO, PANGASINAN
1st Quarter, CY 2022
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration | REMARKS
1 | 8333944 | Construction of Farm to Market Road | Capulaan | 9100000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 9099823.29 | 2022-01-25 | 75 CD | Completed
2 | 8334096 | Construction of Farm to Market Road | San Leon | 3500000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 3499860.82 | 2022-01-25 | 45 CD | Completed
3 | 8334107 | Construction of Farm to Market Road | San Marcelino | 5000000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4999885.18 | 2022-01-25 | 75 CD | Completed
4 | 8334116 | Construction of Farm to Market Road | San Aurelio 1st | 2450000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 2449889.15 | 2022-01-25 | 35 CD | Completed
5 | 8333815 | Purchase of 200 Units of Sprayers Distributed to Tobacco Farmers of Municipality of Balungao, Pangasinan | Balungao | 760000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 750000 | 2022-01-25 | 10 CD | Completed
6 | 8333869 | Purchase of 64 Units Water Pump to Tobacco Farmers Association of Municipality of Balungao, Pangasinan | Balungao | 1280000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 1273600 | 2022-01-25 | 10 CD | Completed
7 | 8338416 | Construction of Farm to Market Road | Esmeralda | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049781.2 | 2022-01-26 | 30 CD | Completed
8 | 8366157 | Purchase of Black Plastic to Tobacco Growers of this municipality | Balungao | 2500000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 2499000 | 2022-01-10 | 15 CD | Completed
9 | 8368265 | Improvement of Municipal Park, Balungao, Pangasinan | Balungao | 3000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2999699.23 | 2022-02-14 | 45 CD | Completed
10 | 8368898 | Fabrication of Doors & Windows Railing at the Municipal Health Office Birthing Clinic Comelec | Balungao | 240000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 239601.82 | 2022-01-14 | 20 CD | Completed
11 | 8368978 | Improvement of Legislative Building | Balungao | 1600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1499940 | 2022-02-14 | 30 CD | Completed
12 | 8368367 | Improvement of Mt. Balungao at Brgy. San Andres | San Andres | 2500000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 2499691.14 | 2022-02-14 | 45 CD | Completed
13 | 8368299 | Construction/Rehabilitation of Balungao Public Market, Balungao, Pangasinan | Balungao | 4000000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 3999717.23 | 2022-02-14 | 60 CD | Completed
14 | 8368510 | Construction of Flood Mitigation Structure of the Municipality of Balunga, Pangasinan | Balungao | 5000000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4999524.23 | 2022-02-14 | 60 CD | Completed
15 | 8364568 | Construction of Farm to Market Road | Pugaro | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049810.38 | 2022-02-10 | 30 CD | Completed
16 | 8338505 | Construction of Farm to Market Road | Poblacion | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049885.15 | 2022-01-26 | 30 CD | Completed
17 | 8349843 | Construction of Farm to Market Road | San Andres | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049923.26 | 2022-02-02 | 30 CD | Completed
18 | 8349905 | Construction of Farm to Market Road | San Joaquin | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049895.23 | 2022-02-02 | 30 CD | Completed
5 | 8349981 | Construction of Farm to Market Road | Capulaan | 9262752 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 9262600.14 | 2022-02-02 | 75 CD | Completed
20 | 8350089 | Construction of Farm to Market Road | Rajal | 5600000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 5599843.03 | 2022-02-02 | 75 CD | Completed
21 | 8350149 | Construction of Farm to Market Road | Angayan Norte | 5600000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 5599861.47 | 2022-02-02 | 75 CD | Completed
22 | 8350248 | Construction of Farm to Market Road | San Leon | 4200000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4199862.97 | 2022-02-02 | 75 CD | Completed
23 | 8350276 | Construction of Farm to Market Road | San Marcelino | 5000000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4999835.07 | 2022-02-02 | 75 CD | Completed
24 | 8364485 | Construction of Farm to Market Road | San Aurelio 1st | 4200000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 4199874.52 | 2022-02-10 | 75 CD | Completed
25 | 8364674 | Construction of Farm to Market Road | Esmeralda | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049815.85 | 2022-02-10 | 30 CD | Completed
26 | 8366022 | Construction of Farm to Market Road | San Andres | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049891.45 | 2022-02-10 | 30 CD | Completed
27 | 8368477 | Livelihood Program (Purchase of Food Stand of this Municipality | Balungao | 736264.6 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 736037.23 | 2022-02-14 | 20 CD | Completed
28 | 8366064 | Construction of Farm to Market Road | San Joaquin | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049887.9 | 2022-02-10 | 30 CD | Completed
29 | 8350046 | Construction of Farm to Market Road | San Raymundo | 8750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 8749826.75 | 2022-02-02 | 75 CD | On-Going
30 | 8333988 | Construction of Farm to Market Road | San Raymundo | 7473423.54 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 7472845.95 | 2022-01-25 | 75 CD | On-Going
31 | 8368213 | Dietary Supplementation of Expectant Mothers & Children of this municipality | Balungao | 700000 | DIAMOND KIIM ENTERPRISES | MANA VITA V. YU | 699900 | 2022-01-14 | 90 CD | On-Going
32 | 8368243 | Electrification Along Pugaro Napudot Road, Balungao, Pangasinan | Balungao | 5500000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 5499678.33 | 2022-02-14 | 60 CD | On-Going
33 | 8364619 | Construction of Farm to Market Road | Angayan Sur | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049898.54 | 2022-02-10 | 30 CD | Not yet started
34 | 8365862 | Construction of Farm to Market Road | Kita-kita | 1050000 | RED MATRIX BUILDERS AND TRADING | XAVIER RAUL CESAR C. TEODORO | 1049804.89 | 2022-02-10 | 30 CD | Not yet started
35 | 8365937 | Construction of Farm to Market Road | Mauban | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049883.37 | 2022-02-10 | 30 CD | Not yet started
36 | 8365970 | Construction of Farm to Market Road | Mabini | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049887.14 | 2022-02-10 | 30 CD | Not yet started
37 | 8365997 | Construction of Farm to Market Road | Poblacion | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049862.05 | 2022-02-10 | 30 CD | Not yet started
38 | 8366044 | Construction of Farm to Market Road | San Aurelio 2nd | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049851 | 2022-02-10 | 30 CD | Not yet started
39 | 833953 | Construction of Farm to Market Road | San Miguel | 7473423.45 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 7473261.75 | 2022-01-25 | 75 CD | Not yet started
40 | 8334020 | Construction of Farm to Market Road | Rajal | 4900000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4899858.31 | 2022-01-25 | 75 CD | Not yet started
41 | 8334038 | Construction of Farm to Market Road | Angayan Norte | 4900000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 4899872.73 | 2022-01-25 | 75 CD | Not yet started
42 | 8334053 | Construction of Farm to Market Road | San Aurelio 3rd | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199883.54 | 2022-01-25 | 75 CD | Not yet started
43 | 8334069 | Construction of Farm to Market Road | San Julian | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199843.81 | 2022-01-25 | 75 CD | Not yet started
44 | 8338335 | Construction of Farm to Market Road | Pugaro | 2450000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 2449890.33 | 2022-01-26 | 35 CD | Not yet started
45 | 8338378 | Construction of Farm to Market Road | Angayan Sur | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049896.48 | 2022-01-26 | 30 CD | Not yet started
46 | 8349871 | Construction of Farm to Market Road | San Aurelio 2nd | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049849.31 | 2022-02-02 | 30 CD | Not yet started
47 | 8350012 | Construction of Farm to Market Road | San Miguel | 8750000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 8749780.76 | 2022-02-02 | 75 CD | Not yet started
48 | 8350173 | Construction of Farm to Market Road | San Aurelio 3rd | 4900000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4899863.03 | 2022-02-02 | 75 CD | Not yet started
49 | 8350231 | Construction of Farm to Market Road | San Julian | 4200000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 4199797.19 | 2022-02-02 | 75 CD | Not yet started
50 | 8338428 | Construction of Farm to Market Road | Kita-kita | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049865.14 | 2022-01-26 | 30 CD | Not yet started
51 | 8338456 | Construction of Farm to Market Road | Mauban | 1050000 | JHI CONSTRUCTION AND SUPPLY | TACLIN I. INIBA | 1049889.14 | 2022-01-26 | 30 CD | Not yet started
52 | 8338484 | Construction of Farm to Market Road | Mabini | 1050000 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | BELLAFLOR V. CORPUZ | 1049901.74 | 2022-01-26 | 30 CD | Not yet started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor