## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER, CY 2022
Province, City or Municipality: BALUNGAO, PANGASINAN
Agency / Address | Projects / Program / Activity Name | Location | Total Cost | Date Started | No. Of Extensions | Target Completion Date | Prpject Status
[7 empty] | % of Completion | Total Cost Incurred to Date | Remarks
LGU Balungao | Construction of Farm to Market Road at Brgy. Capulaan | Capulaan | 9099823.29 | 2022-02-09 |  | 2022-04-24 | 100% | 9099823.29 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Leon | San Leon | 3499860.82 | 2022-02-09 |  | 2022-04-24 | 100% | 3499860.82 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Marcelino | San Marcelino | 499885.18 | 2022-02-08 |  | 2022-04-23 | 100% | 499885.18 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 1st | San Aurelio 1st | 2449889.15 | 2022-02-08 |  | 2022-03-14 | 100% | 2449889.15 | Completed
LGU Balungao | Purchase of 200 Units of Sprayers Distributed to Tobacco Farmers of Municipality of Balungao, Pangasinan | Balungao | 750000 | 2022-02-07 |  | 2022-02-16 | 100% | 750000 | Completed
LGU Balungao | Purchase of 64 Units Water Pump to Tobacco Farmers Association of Municipality of Balungao, Pangasinan | Balungao | 1273600 | 2022-02-07 |  | 2022-02-16 | 100% | 1273600 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Esmeralda | Esmeralda | 1049781.2 | 2022-02-09 |  | 2022-03-10 | 100% | 1049781.2 | Completed
LGU Balungao | Purchase of Black Plastic to Tobacco Growers of this municipality | Balungao | 2499000 | 2022-02-24 |  | 2022-03-10 | 100% | 2499000 | Completed
LGU Balungao | Improvement of Municipal Park, Balungao, Pangasinan | Balungao | 2999699.23 | 2022-02-28 |  | 2022-04-13 | 100% | 2999699.23 | Completed
LGU Balungao | Fabrication of Doors & Windows Railing at the Municipal Health Office Birthing Clinic Comelec | Balungao | 239601.82 | 2022-02-28 |  | 2022-03-19 | 100% | 239601.82 | Completed
LGU Balungao | Improvement of Legislative Building | Balungao | 1499940 | 2022-02-24 |  | 2022-03-25 | 100% | 1499940 | Completed
LGU Balungao | Improvement of Mt. Balungao at Brgy. San Andres | San Andres | 2499691.14 | 2022-02-16 |  | 2022-04-01 | 100% | 2499691.14 | Completed
LGU Balungao | Construction/Rehabilitation of Balungao Public Market, Balungao, Pangasinan | Balungao | 3999717.23 | 2022-02-28 |  | 2022-04-28 |  | 3999717.23 | Completed
LGU Balungao | Construction of Flood Mitigation Structure of the Municipality of Balunga, Pangasinan | Balungao | 4999524.23 | 2022-03-03 |  | 2022-05-01 |  | 4999524.23 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Poblacion | Poblacion | 1049885.15 | 2022-02-11 |  | 2022-03-12 | 100% | 1049885.15 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Andres | San Andres | 1049923.26 | 2022-02-11 |  | 2022-03-12 | 100% | 1049923.26 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Joaquin | San Joaquin | 1049895.23 | 2022-02-15 |  | 2022-03-16 | 100% | 1049895.23 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Capulaan | Capulaan | 9262600.14 | 2022-02-09 |  | 2022-04-24 |  | 9262600.14 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Rajal | Rajal | 5599843.03 | 2022-02-16 |  | 2022-05-01 | 100% | 5599843.03 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Angayan Norte | Angayan Norte | 5599861.47 | 2022-02-15 |  | 2022-04-30 | 100% | 5599861.47 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Leon | San Leon | 4199862.97 | 2022-02-15 |  | 2022-04-30 | 100% | 4199862.97 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Marcelino | San Marcelino | 4999835.07 | 2022-02-16 |  | 2022-05-01 | 100% | 4999835.07 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 1st | San Aurelio 1st | 4199874.52 | 2022-02-23 |  | 2022-05-08 | 100% | 4199874.52 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. Esmeralda | Esmeralda | 1049815.85 | 2022-02-23 |  | 2022-03-24 | 100% | 1049815.85 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Andres | San Andres | 1049891.45 | 2022-02-23 |  | 2022-03-17 | 100% | 1049891.45 | Completed
LGU Balungao | Livelihood Program (Purchase of Food Stand of this Municipality | Balungao | 736037.23 | 2022-02-28 |  | 2022-03-19 | 100% | 736037.23 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Joaquin | San Joaquin | 1049887.9 | 2022-02-24 |  | 2022-03-25 | 100% | 1049887.9 | Completed
LGU Balungao | Construction of Farm to Market Road at Brgy. San Raymundo | San Raymundo | 8749826.75 | 2022-02-16 |  | 2022-05-22 | 45% | 8749826.75 | On-Going
LGU Balungao | Construction of Farm to Market Road at Brgy. San Raymundo | San Raymundo | 7472845.95 | 2022-02-09 |  | 2022-04-24 | 60% | 7472845.95 | On-Going
LGU Balungao | Dietary Supplementation of Expectant Mothers & Children of this municipality | Balungao | 699900 | 2022-02-28 |  | 2022-05-28 | 16% | 699900 | On-Going
LGU Balungao | Electrification Along Pugaro Napudot Road, Balungao, Pangasinan | Balungao | 5499678.33 |  |  |  |  | 5499678.33 | On-Going
LGU Balungao | Construction of Farm to Market Road at Brgy. Angayan Sur | Angayan Sur | 1049898.54 |  |  |  |  | 1049898.54 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Kita-kita | Kita-kita | 1049804.89 |  |  |  |  | 1049804.89 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Mauban | Mauban | 1049883.37 |  |  |  |  | 1049883.37 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Mabini | Mabini | 1049887.14 |  |  |  |  | 1049887.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Poblacion | Poblacion | 1049862.05 |  |  |  |  | 1049862.05 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 2nd | San Aurelio 2nd | 1049851 |  |  |  |  | 1049851 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Miguel | San Miguel | 7473261.75 |  |  |  |  | 7473261.75 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Rajal | Rajal | 4899858.31 |  |  |  |  | 4899858.31 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Angayan Norte | Angayan Norte | 4899872.73 |  |  |  |  | 4899872.73 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 3rd | San Aurelio 3rd | 4199883.54 |  |  |  |  | 4199883.54 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Julian | San Julian | 4199843.81 |  |  |  |  | 4199843.81 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Pugaro | Pugaro | 2449890.33 |  |  |  |  | 2449890.33 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Angayan Sur | Angayan Sur | 1049896.48 |  |  |  |  | 1049896.48 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 2nd | San Aurelio 2nd | 1049849.31 |  |  |  |  | 1049849.31 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Miguel | San Miguel | 8749780.76 |  |  |  |  | 8749780.76 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Aurelio 3rd | San Aurelio 3rd | 4899863.03 |  |  |  |  | 4899863.03 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. San Julian | San Julian | 4199797.19 |  |  |  |  | 4199797.19 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Kita-kita | Kita-kita | 1049865.14 |  |  |  |  | 1049865.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Mauban | Mauban | 1049889.14 |  |  |  |  | 1049889.14 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Mabini | Mabini | 1049901.74 |  |  |  |  | 1049901.74 | Not yet started
LGU Balungao | Construction of Farm to Market Road at Brgy. Pugaro | Pugaro | 1049810.38 |  |  |  |  | 1049810.38 | Not yet started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor