## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2021
Province, City or Municipality: BALUNGAO, PANGASINAN
Agency / Address | Projects / Program / |  |  |  |  | Target | Prpject Status
| Activity Name | Location | Total | Date | No. of | Completion | % of | Total
|  |  | Cost | Started | Extensions | Date | Completion | Cost Incurred | Remarks
to Date
LGU-BALUNGAO | Construction of Cabaroan SWIP at Brgy. Esmeralda | Esmeralda | 12999909.44 | 2021-11-05 | N/A | 2022-04-23 | 100 | 12999909.44 | Completed
LGU-BALUNGAO | Construction of 10 Units Egipto SFR & 10 units at San Andres & San Aurelio 1st | San Andres & San Aurelio 1st | 2000000 | 2021-11-05 | N/A | 2021-12-04 | 100 | 2000000 | Completed
LGU-BALUNGAO | Procurement of Conference Table, Chairs & Sounds System to SK Federation Building at Brgy. Poblacion, Balungao, pangasinan | Balungao | 200000 | 2021-11-25 | N/A | 2021-11-30 | 100 | 200000 | Completed
LGU-BALUNGAO | Improvement of Agriculture Office (Extension at the Front & Back of the Building) at Brgy. Poblacion | Balungao | 749992 | 2021-12-01 | N/A | 2021-12-20 | 100 | 749992 | Completed
LGU-BALUNGAO | Installation of Water Source & Water System (SK Federation Building, Senior Citizen Federation Building, ECCD Building, San Leeon Public Market of the Municipality Balungao, Pangasinan | Balungao | 369993 | 2021-12-01 | N/A | 2021-12-20 | 100 | 369993 | Completed
LGU-BALUNGAO | Improvement of the Electrical Facilities Separation of Metering Box: SK Federation Building, Senior Citizen Federation Building, ECCD Building, SB Building, PNP Building Municipal Gymnasium | Balungao | 299998 | 2021-12-01 | N/A | 2021-12-20 | 100 | 299998 | Completed
LGU-BALUNGAO | Purchase of Office Supplies ICT, Medical Supplies & Other Supplies & Materials to be used by the different offices & School of this Municipality | Balungao | 1398165.57 | 2021-12-03 | N/A | 2021-12-07 | 100 | 1398165.57 | Completed
LGU-BALUNGAO | Purchase of ICT Equipments to be used by the different Offices & Schools of this muncipality | Balungao | 315991.5 | 2021-12-03 | N/A | 2021-12-07 | 100 | 315991.5 | Completed
LGU-BALUNGAO | Construction of Flood Mitigation (Phase II) | Balungao | 2524995 | 2021-12-06 | N/A | 2021-12-30 | 100 | 2524995 | Completed
LGU-BALUNGAO | Improvement of Isolation Facility | Poblacion | 699994 | 2021-12-06 | N/A | 2021-12-30 | 100 | 699994 | Completed
LGU-BALUNGAO | Constrution of Slope Protection at Sitio Langto & Sitio Decrito | Esmeralda | 1548668 | 2021-12-06 | N/A | 2022-01-04 | 100 | 1548668 | Completed
LGU-BALUNGAO | Construction of Material Recovery Facility Expansion | Poblacion | 199996 | 2021-12-06 | N/A | 2021-12-20 | 100 | 199996 | Completed
LGU-BALUNGAO | Improvement of RHU Facilities (Extension at the Right Side of the Municipal Health Officer & Birthing Clinic & Water System Improvement) of this municipality | Poblacion | 1374992 | 2021-12-06 | N/A | 2021-12-30 | 100 | 1374992 | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| ENGR. GLACE L. OSOTEO |  |  |  |  | HON. MARIA THERESA R. PERALTA
| MPDC |  |  |  |  | Municipal Mayor