## Sheet1
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
3RD QUARTER CY 2023
Region |  | REGION I
Province |  | PANGASINAN
City / Municipality |  | BALUNGAO
Program / Project |  |  | Location | Total Cost | Sdate Started | Target | PROJECT STATUS |  | Number of | REMARKS
[6 empty] | Completion | % of Completion | Total Cost | Extension (if Any)
[6 empty] | Date |  | Incurred to Date
I. SOCIAL SERVICES
* | Dietary Supplementation of |  | Balungao | 775576.8 | 2023-04-13 |  |  | 598350 |  | on going
Expectant mothers and children
* | Demolition of Municipal Gym and |  | Poblacion, Balungao | 9000000 | Sept. 13, 2023 |  |  |  |  | on going
| Construction of Apolinario Mbini |  | Pangasinan
II. ECONOMIC SERVICES
* | Establishment of Balungao |  | Poblacion, Balungao | 3500000 | 2023-04-21 | 2023-06-04 | 100% | 3499750 |  | Completed
Coffee Production
* | I start Program (LGU-Counterpart) |  | Balungao | 2000000 | 2023-04-19 | 2023-05-18 | 100% | 1999750 |  | Completed
* | Establishment of Goat Academy |  | Balungao | 5000000 | 2023-04-17 | 2023-05-17 | 100% | 4999820 |  | Completed
* | Rehabilitation of Farm to Market |  | Rajal, Balungao | 5000000 | 2023-04-17 | 2023-05-16 | 100% | 4999650 |  | Completed
Road
III. OTHER SERVICES
* | Reforestation Program |  | Mabini, Balungao | 5000000 | 2023-04-13 | 2023-04-22 | 100% | 499915 |  | Completed
CERTIFIED CORRECT:
ALMEDA O. DE VENECIA
Municipal Accountant