## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2024
PROVINCE: | PANGASINAN |  | QUARTER: | 2
CITY/MUNICIPALITY: | BALUNGAO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
I. SOCIAL SERVICES
Dietary Supplementation of Expectant Mothers and Children | Balungao, Pangasinan | 827674.6 | 2024-04-01 |  | 91% | 406300 |  | 91% Complete
Energy Conservation Program | Balungao, Pangasinan | 1000000 | [5 empty] | Not yet started
Water Quality Management and Monitoring Program | Balungao, Pangasinan | 100000 | [5 empty] | Not yet started
Solid Waste Management Program | Balungao, Pangasinan | 200000 | [5 empty] | Not yet started
II . ECONOMIC SERVICES
Construction of Restrooms and Shower Area at MBHCSR | Balungao, Pangasinan | 3500000 | [5 empty] | Not yet started
Balungao Coffee Production | Balungao, Pangasinan | 1750000 | [5 empty] | Not yet started
iSTART Program (LGU-Counterpart) - Water Treatment at MBHCSR | Balungao, Pangasinan | 2000000 | [5 empty] | Not yet started
Goat Academy | Balungao, Pangasinan | 2000000 | [5 empty] | Not yet started
LGU-Counterpart - Rice Processing Center | Balungao, Pangasinan | 5000000 | [5 empty] | Not yet started
Construction of Farm to Market Roads | Balungao, Pangasinan | 3000000 | [5 empty] | Not yet started
LGU Counterpart Fund PRDP Project (Potable Water Supply) | Balungao, Pangasinan | 1000000 | [5 empty] | Not yet started
III. OTHER SERVICES
Rehabilitation of the Public Plaza and Auditorium | Balungao, Pangasinan | 7000000 | [5 empty] | Not yet started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ALMEDA O. DE VENECIA |  |  |  | MARIA THERESA R. PERALTA
| Municipal Accountant |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1