## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1

## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2025
PROVINCE: | PANGASINAN |  | QUARTER: | 1
CITY/MUNICIPALITY: | BALUNGAO
PROJECTS STATUS
Project/Program/Activity Name | Location | Total Cost | Date Started | Target Completion | % of Completion | Totals Cost Incurred to Date | Number of Extention (if any) | REMARKS
I. SOCIAL SERVICES
Defacation Program | Balungao, Pangasinan | 1999900 | 2025-02-18 | 2025-06-30 |  |  |  | Ongoing
Dietary Supplies Expectant Mother | Balungao, Pangasinan | 175500 | 2025-02-18 | 2025-06-30 | 17.57% | 175500 |  | Ongoing
Improvement of E-Library | Balungao, Pangasinan | 998000 | 2025-02-24 | 2025-03-24 | 100% | 998000 |  | Completed
Improvement Cultural/ Sports Center | Poblacion, Balungao Pangasinan | 5999715.3 | 2025-02-05 | 2025-03-23 | 100% | 5999715.3 |  | Completed
II . ECONOMIC SERVICES
Improvement of Slaughter House | Poblacion, Balungao Pangasinan | 0 | - | - | - | - | - | Not Yet Started
Gender Sensitive/ Senior Citizen & PWD Friendly Restroom New Cemetery | - | 1028978.78 | 2025-02-17 | 2025-04-03 | 100% | 1028978.78 |  | Completed
Construction Road Ongoing & Perimeter Fence- Goat Academy | - | 0 | - | - | - | - | - | Not Yet Started
Construction of Carabao Housing | - | 0 | - | - | - | - |  | Not Yet Started
Construction of Motorpool With stockroom-Goat Academy | - | 0 | - | - | - | - |  | Not Yet Started
Coffee Production | - | 0 | - | - | - | - |  | Not Yet Started
Goat Academy | - | 0 | - | - | - | - |  | Not Yet Started
III. OTHER SERVICES
Improvement of Public Audithorium Apolinario Mabini | Poblacion, Balungao Pangasinan | 3999712.74 | 2025-01-29 | 2025-03-28 | 100% | 3999712.74 |  | Completed
Totals |  | 14201806.82 |  |  |  | 12201906.82
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ALMEDA O. DE VENECIA |  |  |  | MARIA THERESA R. PERALTA
| Municipal Accountant |  |  |  | Local Chief Executive